## hzrdmgmt
OHA ID | Mode | System | Subsystem | Date Created | Task Desc_Full | Hazard Description_Full | Probability of Occurence | Severity of Hazard | Probability of Occurrence_ | Planned Completion Date | Resolution Date | Status | Assigned To | Severity of Hazard_ | Hazard Risk Index | Hazard Risk Index_ | Source of Hazard Identification
OHA_00001 | Support Services | Communications | Radios | 2010-12-09 | There are dead spots where radio communication is not possible throughout the rail system. | Police officers and track employees are unable to request assistance, call out locations, or report emergencies. SOP's cannot be followed. Situations cannot be reported, | Frequent | Critical | Not Rated |  |  | In Analysis | Mayfield, Gerald | Not Rated | 2A - Unacceptable |  | Employee Complaints
OHA_00002 | Rail | Rail Car Lift | Drive motor | 2010-12-09 | Use a rail car lift to perform routine maintenance work. | Output module has driven down the motor without a command. | Occasional | Critical | Not Rated |  |  | In Analysis | Kelley, Scott E. | Not Rated | 2C - Undesirable - Management (ESC) decision |  | Incident
OHA_00003 | Bus | Rules and Procedures | Bus Stop | 2011-02-04 | Assess the current bus stop location - determine if it is safe and lawful to have buses converge into the driving lane from the Right Turn only lane. Assess the current signage to ensure buses are lawful. Consider elimination of stop. | Be advised that currently a safety issue exists along a portion of the route being served by the metrobus routes 10B, 23A, 23C. The location of this safety hazard is N. Glebe Road and Henderson Road in Arlington County (VA). In the southbound direction at this location there is a (service) bus stop within the confines of a right turn only lane. (As designated by pavement markings) Once this stop is serviced by the above routes the operator(s) are forced to disobey pavement markings and attempt to merge left back into traffic instead of turning right as indicated by lane usage. This is a violation of the code of Virginia § 46.2-830. Uniform marking and signing of highways) furthermore the operators of these routes are also compelled to violate one of the principles of the WMATA training department which reinforces that “operators should never change lanes within an intersection”. Travelling along N. Glebe Road prior to this intersection N. Glebe Rd. has 4 lanes ( 2 forward travel, 1right turn only, and 1 parking lane ) after this intersection N. Glebe Rd. has just 2 forward travel lanes. The placement of this stop must have surely been overlooked when it came to the safety of all concerned. The placement of this stop, as it exists now, represents a clear and present danger to the safety of the public. | Remote | Marginal | Improbable | 2011-02-28 |  | Assigned | Gilbert, Raquelle | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | Employee Tracy Gray
OHA_00004 | Bus | Rules and Procedures | Vehicle | 2011-03-31 | Assess the current Pre-trip Inspection Form and Bus Condition Checklist Form - determine if it is a safe to observe the Amerex Fire Suppression System's control module. Consider adding module to the form. | Be advised that currently a safety issue exists for monitoring only in the PM of the Amerex Fire Suppression System's control module by the Cleaner Shifter. | Remote | Marginal | Remote | 2011-04-29 |  | Assigned | Gilbert, Raquelle | Marginal | 3D - Acceptable with ESC review | 3D - Acceptable with ESC review | Safety Officers Cummings, Medley, and McNeil
OHA_00005 | Rail | Railcar | Brakes | 2012-07-02 | No rollback protection on 4000-series cars presents potential for exeessive train rollback while stopped on grade. Installation of roll back protection in 4000 series cars during mid-life modernization/overhaul. 3/16/10--Installation will be independent of modernization/overhaul. Design to start immediately. | Excessive train rollback while stopped on grade. | Remote | Catastrophic | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 1/17/07 Response to NTSB: R-06-1d NTSB2
OHA_00006 | Rail | Railcar | Doors | 2012-08-06 | No external door release handle on all series of cars for emergency services to access stationary train without a key causes an inability to access vehicle from the outside in the event of an emergency if a key is not available. Provide external door release handle on all series of cars for emergency services to access stationary train without a key. 10/2/07--Will install if determined to be feasible. | Inability to access vehicle from the outside in the event of an emergency if a key is not available. | Remote | Catastrophic | Improbable | 2013-04-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 1/17/07 Response to NTSB: R-06-5 NTSB5
OHA_00007 | Rail | Rules, Regulations, Procedures | Drug and Alcohol | 2012-02-13 | WORX--Re-establish/Fully implement the Poster Program relating to Drug and Alcohol and Employee Assistance Program information. Inadequate communication of Drug and Alcohol and Employee Assistance Program information. | Inadequate communication of Drug and Alcohol and Employee Assistance Program information. | Occasional | Negligible | Remote | 2011-11-15 | 2011-11-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | 2007 Internal Audits IA7-7
OHA_00008 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-05-09 | While WMATA has advanced some prototype Configuration Management efforts, there does not appear to be an overall authority-wide policy, procedure, or plan to address the requirement in the SSPP for Configuration Management. Safety issue or concern not properly identified, reported, assessed, or mitigated. WMATA is planning to implement a Configuration Management Program. Pilot project completed by June 2008. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2011-06-01 | 2011-06-01 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2007 Triennial #4
OHA_00009 | Rail | Rules, Regulations, Procedures | Construction Safety and Environmental | 2012-05-09 | WMATA should expand its Construction Safety and Environmental Manual to include construction security considerations. Current security system may not be sufficient. | Current security system may not be sufficient. | Remote | Marginal | Improbable | 2011-06-01 | 2011-06-01 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2007 Triennial #6
OHA_000010 | Rail | Rules, Regulations, Procedures | RTRA Utility Supervisor Training Program | 2012-02-13 | The RTRA Utility Supervisor Training Program Description and Guidelines document should be updated to reflect the recent organizational changes at WMATA, as well as to reflect the names of current instructors for each course. Inadequate training of rail personnel. | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2011-09-30 |  | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2007 Triennial #16
OHA_000011 | Rail | Rules, Regulations, Procedures | Medical Recertification Requirements for Rail Operators | 2011-09-28 | There is no medical recertification requirement for rail operators, even though bus operators do have such a requirement. This could result in a Train operator working with diminished capacity. | Train operator working with diminished capacity. | Remote | Catastrophic | Remote | 2008-06-01 | 2011-07-19 | Completed | McCoy, Darren | Marginal | 1D - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | 2007 Triennial #17
OHA_000012 | Rail | Rules, Regulations, Procedures | Drug and Alcohol Policy | 2012-07-02 | Elevator and escalator mechanics, as well as Station Managers, are not subject to any form of random drug and alcohol testing. Elevator and escalator mechanics, as well as Station Managers are working with diminished capacity. | Elevator and escalator mechanics, as well as Station Managers are working with diminished capacity. | Occasional | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2007 Triennial #18
OHA_000013 | Rail | Facilities | Prints of Interlocking Locations | 2012-08-06 | The prints in a sample of interlocking locations were in the same tattered, ripped, and disorganized condition noted in TOC's 2004 triennial review. This could result in an inability to respond quickly and appropriately during an emergency. The Infrastructure Renewal Group (IRPG) is currently managing the reproduction of interlocking location prints utilizing the engineering services of P^2D. Expected completion in five (5) years. | Inability to respond quickly and appropriately during an emergency. | Remote | Critical | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2D - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2007 Triennial #25
OHA_000014 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-08-06 | The availability of Record Drawings needs to be improved of a safety issue or concern may not be properly identified, reported, assessed, or mitigated. WMATA is in the process of developing a program to access information located in the Document Content Server through a graphically displayed, user friendly Metro station map. The fully funded project is being coordinated through the Office of Information | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2007 Triennial #36
OHA_000015 | Rail | Stations | Elevators & Escalators | 2012-05-01 | The preventive maintenance inspections (PMIs) reviewed for eight escalators and three elevators (two years' record each) showed significant variation in schedule attainment, including many late inspections. This could result in elevators or escalators not being available in the event of an emergency - particularly at Forest Glen Station. Most units are on a 30 day PMI schedule; expect ELES, inside, platform, and Westinghouse units, which are on a 45 day schedule. This schedule date is the goal, however, circumstances such as timing around special events, repairs, CIPs and mechanic available. | Elevators or escalators not available in the event of an emergency - particularly at Forest Glen Station. | Occasional | Catastrophic | Occasional | 2012-04-30 | 2012-04-30 | Completed | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | 2007 Triennial #45
OHA_000016 | Rail | Rules, Regulations, Procedures | PMI Schedules | 2012-05-01 | Monthly (B), quarterly (C) and annual (E) ELES PMIs do not always occur in a predictable fashion. As a result, personnel may not implement proper safety related procedures. The implementation of the new Maximo maintenance system was not as smooth as desired and created inconsistencies with the PMI schedule. The PMI schedules are now becoming more logical and consistent as bugs and issues are worked out. ELES will continue. | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Improbable | 2012-04-30 | 2012-04-30 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2007 Triennial #46
OHA_000017 | Rail | ROW | Wayside Warning Devices | 2012-01-31 | Promptly implement appropriate technology that will automatically alert wayside workers of approaching trains and will automatically alert train operators when approaching areas with workers on or near the tracks. Failure to do so could result in wayside worker not neing alerted to oncoming train and/or operator is not alerted to workers on track. WMATA will evaluate available technology and new approaches for automatically alerting wayside workers of approaching trains and will automatically alert train operators when approaching areas with workers on or near the tracks. | Wayside worker is not alerted to oncoming train and/or operator is not alerted to workers on track. | Occasional | Catastrophic | Remote | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 1C - Unacceptable | 2D - Undesirable - Management (ESC) decision | Eisenhower Ave./DuPont Circle TW4
OHA_000018 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 16, Employee Training | 2011-09-28 | Revise the SSPP to reflect the reality that existed regarding "refresher training" and recertification of Operators. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Improbable | 2011-02-28 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Internal Safety Audit IA8-1
OHA_000019 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 13, Rules and Procedures Compliance | 2011-09-28 | Several processes/techniques are in place to provide for rule compliance; the SSPP is silent in that regard. Recommend SSRM and Operations review what processes/techniques are in place and include them in the SSPP. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Improbable | 2011-02-28 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Internal Safety Audit IA8-2
OHA_000020 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 18, Employee and Contractor Safety Program | 2011-09-28 | Revise the SSPP to specify the types of Medical Surveillance in place and required at WMATA. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Improbable | 2011-02-28 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Internal Safety Audit IA8-3
OHA_000021 | Rail | Rules, Regulations, Procedures | Hearing Conservation Program | 2012-01-31 | Develop and fully implement a WMATA Hearing Conservation Program that is compliant with OSHA requirements. Workers subjected to loud sounds without proper hearing protection. | Workers subjected to loud sounds without proper hearing protection. | Occasional | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | Internal Safety Audit IA8-4
OHA_000022 | Rail | Rules, Regulations, Procedures | OSHA 10-hour training | 2011-09-28 | Provide the OSHA 10-hour training to the three individuals hired as ARs since the last time the course was offered. Failure to do so may result in inadequate training. | Inadequate training. | Remote | Negligible | Improbable | 2011-03-16 | 2011-03-16 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Internal Safety Audit IA8-5
OHA_000023 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Elment 3, Management Structure | 2011-09-28 | Revise the SSPP to note that QA auditors now report to the divisions they are responsible for auditing. Failure to do so could result in safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Improbable | 2011-02-28 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Internal Safety Audit IA8-7
OHA_000024 | Rail | Rules, Regulations, Procedures | Evaluation of Proposed System Improvements | 2012-07-02 | Establish a process, including a single point of responsibility, to prompt timely evaluation and action on proposed safety improvements that are identified as a result of accident and derailment investigations and related research projects. Failure to do so could result in personnel not implementing proper safety related procedures. | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | NTSB MV Derailment report MV4
OHA_000025 | Rail | Train Protection System | ATC Testing Programs | 2012-01-31 | Develop a program to periodically determine that electronic components in your train control system are performing within design tolerances. Failure to do so could result in equipment operating outside design tolerances. | Equipment operating outside design tolerances. | Remote | Negligible | Improbable | 2012-12-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | NTSB Fort Totten Collision preliminary report FT2
OHA_000026 | Rail | Rules, Regulations, Procedures | Accident Investigation Procedure | 2012-02-14 | Revise Accident/Incident Investigation Procedures as the last revision is dated April 26, 2006. Failure to do so may result in personnel do not implement proper safety related procedures. | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2011-11-15 |  | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2009 Internal Safety Audit ISA9-2
OHA_000027 | Rail | Rules, Regulations, Procedures | Track Standards Manual | 2012-02-14 | Revise the WMATA Track Standards Manual to provide clear definitions of track conditions encountered by Track Walkers with the goal of assuring uniform interpretations of how they should handle each condition. Failure to do so may result in safety issue or concern not being properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Improbable | 2011-06-15 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Bethesda derailment report 6/1/09 #1
OHA_000028 | Rail | Rules, Regulations, Procedures | Coordination meetings between Inspection, Maintenance and Structures | 2012-02-13 | Consider reinstating periodic meetings between Inspection, Maintenance and Structures personnel to improve the efficiency of the condition reporting and corrective action process. Failure to do so may result in safety issue or concern not being properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Marginal | Improbable | 2011-06-15 | 2011-06-28 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | Bethesda derailment report 6/1/09 #2
OHA_000029 | Rail | Rules, Regulations, Procedures | MAXIMO | 2012-02-13 | TSSM needs to develop a standard for prioritizing track condition progression and escalation within MAXIMO. Failure to do so may result in safety issue or concern not being properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Remote | 2011-06-15 | 2011-06-28 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Bethesda derailment report 6/1/09 #3
OHA_000030 | Rail | Rules, Regulations, Procedures | Track Inspection Discrepancy Feedback Loop | 2012-02-13 | Create a "discrepancy feedback loop" that informs Track Walkers of corrective actions taken, or to be taken, resulting from the track conditions that they report. Inadequate verification of resolution of track issues. | Inadequate verification of resolution of track issues. | Remote | Negligible | Improbable | 2011-06-15 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Bethesda derailment report 6/1/09 #4
OHA_000031 | Rail | Rules, Regulations, Procedures | Follow-up Track Inspections | 2012-01-27 | Consider increasing the number of follow-up inspections performed by Managers to support Track Walker's findings and help set priorities for corrective actions. These follow-up inspections should be documented. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2011-08-31 | 2011-06-28 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Bethesda derailment report 6/1/09 #5
OHA_000032 | Rail | Rules, Regulations, Procedures | Track Inspection Results Prioritization | 2012-02-01 | Revise and enhance the system for categorizing poor track conditions focusing on their impact to the railroad and importance for corrective action. Assure that the system brings attention to the progression of a known poor condition. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2011-08-31 | 2011-08-31 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Bethesda derailment report 6/1/09 #6
OHA_000033 | Rail | Rules, Regulations, Procedures | Defect Monitoring | 2012-04-18 | Create/revise procedures that monitor, automatically, all yellow defects after a set period of thirty (30) days, causing the MMMS to generate an update condition assessment. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Improbable | 2011-08-31 | 2011-08-31 | Completed | McCoy, Darren | Catastrophic | 1C - Unacceptable | 1E - Acceptable with ESC review | Bethesda derailment report 6/1/09 #7
OHA_000034 | Rail | Rules, Regulations, Procedures | Track Inspection Water Intrusion Corrective Actions | 2012-01-27 | Review the effectiveness of the water intrusion corrective action programs and identify the resources necessary for improvement. WMATA employee/equipment exposure to hazards due to inadequate corrective action of water intrusion issues. | WMATA employee/equipment exposure to hazards due to inadequate corrective action of water intrusion issues. | Remote | Critical | Improbable | 2011-08-31 | 2011-06-28 | Completed | McCoy, Darren | Critical | 2D - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | Bethesda derailment report 6/1/09 #8
OHA_000035 | Rail | Rules, Regulations, Procedures | Track Inspection Track Walker Training Programs | 2012-02-13 | Enhance Track Walker training to assure a uniform understanding of the various track conditions encountered by Track Walkers on a daily basis. Attempt to reduce the need for "judgment calls" that could have a negative impact on the railroad. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2011-06-15 | 2011-06-28 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Bethesda derailment report 6/1/09 #9
OHA_000036 | Rail | Rules, Regulations, Procedures | Track Inspection Ultrasoni Inspection Oversight | 2012-02-13 | TSSM must provide competent oversight of the ultrasonic inspection contract by training personnel, using outside consultants, or a combination of both. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Negligible | Improbable | 2011-08-31 | 2011-06-22 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Bethesda derailment report 6/1/09 #10
OHA_000037 | Rail | Rules, Regulations, Procedures | Standard Operating Procedure 32 | 2012-04-18 | Standard Operating Procedure (SOP) 32 needs to be revised to address the Operator's close-in procedures relating to the observation of track conditions. Failure to identify safety issue or concern related to track condition. | Failure to identify safety issue or concern related to track condition. | Occasional | Marginal | Remote | 2012-01-31 | 2012-01-31 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Bethesda derailment report 6/1/09 #11
OHA_000038 | Rail | Rules, Regulations, Procedures | Disciplinary Action of Train Operators | 2011-09-28 | RTRA take corrective action with 902 Train Operator to prevent the reoccurrence of this type of incident. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2009-12-31 | 2011-06-14 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | WFC WMATA report 1/28/10 #1
OHA_000039 | Rail | Rules, Regulations, Procedures | Yard Operations Communications Protocols | 2011-09-28 | Issue Yard Operations directives on communication protocol and activities to include reducing speed in yards to 10 mph on a trial basis. Inadequate communication of safety related issues. | Inadequate communication of safety related issues. | Occasional | Marginal | Remote | 2009-12-31 | 2010-06-14 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | WFC WMATA report 1/28/10 #2
OHA_000040 | Rail | Rules, Regulations, Procedures | Yard Operations Communications Quality Control Plan | 2011-09-28 | Develop quality control plan that includes random audits on yard communications, safety stops and rolling/ rolling brake test for compliance in the yards. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Remote | 2010-01-31 | 2010-06-14 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | WFC WMATA report 1/28/10 #3
OHA_000041 | Rail | Rules, Regulations, Procedures | Quality Checks of Yard and Tower Operations | 2011-09-28 | Implement requirement for Chief Operations Supervisor to conduct random quality checks of Yard and Tower Operations twice a week and submit reports (email format acceptable). Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Remote | 2010-01-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | WFC WMATA report 1/28/10 #4
OHA_000042 | Rail | Rules, Regulations, Procedures | Train Operator Driver Lincenses | 2011-09-28 | Develop program for regular review of valid driver's licenses of all train operators. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Marginal | Improbable | 2010-04-30 | 2011-07-19 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | WFC WMATA report 1/28/10 #5
OHA_000043 | Rail | Rules, Regulations, Procedures | Fitness For Duty Program | 2011-09-29 | Develop Fitness for Duty program that includes regular medical exams of all Train Operators. Train operator working with diminished capacity. | Train operator working with diminished capacity. | Remote | Catastrophic | Remote | 2010-06-30 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4D - Acceptable without review | WFC WMATA report 1/28/10 #6
OHA_000044 | Rail | Rules, Regulations, Procedures | Fitness For Duty Program | 2012-07-02 | Develop guidelines on addressing reports from front line employees concerning fatigue. The guidelines shall give specific questions to ask and appropriate actions taken based on responses from the employee. Train operator working with diminished capacity. | Train operator working with diminished capacity. | Remote | Catastrophic | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | WFC WMATA report 1/28/10 #7
OHA_000045 | Rail | Rules, Regulations, Procedures | SOP 29 - Blue Flagging | 2011-09-29 | Request Rule Book Committee review SOP 29 on Blue Flagging procedures. Inadequate communication of safety related issues. | Inadequate communication of safety related issues. | Remote | Catastrophic | Remote | 2010-06-30 | 2011-06-14 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4D - Acceptable without review | WFC WMATA report 1/28/10 #8
OHA_000046 | Rail | Rules, Regulations, Procedures | Train Operation Propulsion Rates | 2011-09-29 | Request Rule Book Committee to modify/create rule stipulating only P1 or P2 propulsion rates shall be used to move trains when zero speed commands are displayed on the console or while in the yard unless specifically authorized. Potential safety issue results from inadequate or incomplete documentation. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Catastrophic | Remote | 2010-06-30 | 2011-06-14 | Completed | McCoy, Darren | Negligible | 1C - Unacceptable | 4D - Acceptable without review | WFC WMATA report 1/28/10 #9
OHA_000047 | Rail | Train Protection System | ATC Carborne/Wayside Systems | 2011-09-29 | Evaluate feasibility to implement car borne or wayside systems to limit acceleration to P1 to P2 propulsion rates when zero speed readouts are present. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2010-06-30 | 2011-07-19 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | WFC WMATA report 1/28/10 #10
OHA_000048 | Rail | Train Protection System | Track Occupancy Data | 2012-01-31 | Take action to enhance the safety redundancy of your train control system by evaluating track occupancy data on a real-time basis in order to detect losses in track occupancy and automatically generate alerts. Alerts should prompt actions that include immediately stopping train movements or implementing appropriate speed restrictions to prevent collisions. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Occasional | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | Ft. Totten NTSB report 8/10/10 R-09-6
OHA_000049 | Rail | Rules, Regulations, Procedures | Safety Policies and Procedures | 2012-02-13 | Elevate the safety oversight role of the Washington Metropolitan Area Transit Authority Board of Directors by (1) developing a policy statement to explicitly and publicly assume the responsibility for continual oversight of system safety, (2) implementing processes to exercise oversight of system safety, including appropriate proactive performance metrics, and (3) evaluating actions taken in response to National Transportation Safety Board and Federal Transit Administration recommendations, as well as the status of open corrective action plans and the results of audits conducted by the Tri-State Oversight Committee. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2011-04-15 | 2011-04-26 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Ft. Totten NTSB report 8/10/10 R-10-7
OHA_000050 | Rail | Train Protection System | Generation 2 General Railway Signal Company Audit Frequency Track Circuit Modules | 2012-07-02 | Because of the susceptibility to pulse-type parasitic oscillation that can cause a loss of train detection by the Generation 2 General Railway Signal Company audio frequency track circuit modules, establish a program to permanently remove from service all of these modules within the Metrorail system. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Occasional | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | Ft. Totten NTSB report 8/10/10 R-10-8
OHA_000051 | Rail | Train Protection System | Track Circuit Modules | 2012-01-27 | Establish periodic inspection and maintenance procedures to examine all audio frequency track circuit modules within the Metrorail system to identify and remove from service any modules that exhibit pulse-type parasitic oscillation. Potential loss of train detection by audio frequency track circuit modules within the Metrorail system. | Potential loss of train detection by audio frequency track circuit modules within the Metrorail system. | Occasional | Catastrophic | Remote | 2011-09-30 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 1C - Unacceptable | 4D - Acceptable without review | Ft. Totten NTSB report 8/10/10 R-10-9
OHA_000052 | Rail | Rules, Regulations, Procedures | Metrorail Technical Bulletins and Safety Information | 2012-08-06 | Review the process by which Metrorail technical bulletins and other safety information are provided to employees and revise that process as necessary to ensure that (1) employees have received the information intended for them, (2) employees understand the actions to be taken in response to the information, and (3) employees take the appropriate actions. Inadequate communication of safety related issues. | Inadequate communication of safety related issues. | Remote | Marginal | Remote | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3D - Acceptable with ESC review | Ft. Totten NTSB report 8/10/10 R-10-10
OHA_000053 | Rail | ROW | Wayside Maintenance Communication Systems | 2012-01-31 | Completely remove the unnecessary Metrorail wayside maintenance communication system to eliminate its potential for interfering with the proper functioning of the train control system. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Occasional | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | Ft. Totten NTSB report 8/10/10 R-10-11
OHA_000054 | Rail | Train Protection System | Automatic Train Control Safety Analysis | 2012-01-31 | Conduct a comprehensive safety analysis of the Metrorail automatic train control system to evaluate all foreseeable failures of this system that could result in a loss of train separation, and work with your train control equipment manufacturers to address in that analysis all potential failure modes that could cause a loss of train detection, including parasitic oscillation, cable faults and placement, and corrugated rail. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Probable | Catastrophic | Remote | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1B - Unacceptable | 1D - Undesirable - Management (ESC) decision | Ft. Totten NTSB report 8/10/10 R-10-12
OHA_000055 | Rail | Train Protection System | Automatic Train Control Design, Operation and Maintenance | 2012-01-31 | Based on the findings of the safety analysis recommended in R-10-12 incorporate the design, operational, and maintenance controls necessary to address potential failures in the automatic train control system. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1C - Unacceptable | 1E - Acceptable with ESC review | Ft. Totten NTSB report 8/10/10 R-10-13
OHA_000056 | Rail | Train Protection System | Cable Insulation Resistance Testing | 2012-07-02 | Implement cable insulation resistance testing as part of Metrorail’s periodic maintenance program. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Occasional | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | Ft. Totten NTSB report 8/10/10 R-10-14
OHA_000057 | Rail | Rules, Regulations, Procedures | Coordination with the Tri-State Oversight Committee | 2012-07-02 | Work with the Tri-State Oversight Committee to satisfactorily address the recommendations contained in the Federal Transit Administration’s March 4, 2010, final report of its audit of the Tri-State Oversight Committee and the Washington Metropolitan Transit Authority. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Critical | Remote | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2D - Undesirable - Management (ESC) decision | Ft. Totten NTSB report 8/10/10 R-10-15
OHA_000058 | Rail | Train Protection System | Train Onboard Recorders | 2012-07-02 | Require that your safety department; representatives of the operations, maintenance, and engineering departments; and representatives of labor organizations regularly review recorded operational data from Metrorail train onboard recorders and the Advanced Information Management system to identify safety issues and trends and share the results across all divisions of your organization. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Remote | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Ft. Totten NTSB report 8/10/10 R-10-16
OHA_000059 | Rail | Rules, Regulations, Procedures | Safety Reporting Systems (Hotline) | 2012-01-31 | Develop and implement a non-punitive safety reporting program to collect reports from employees in all divisions within your organization, and ensure that the safety department; representatives of the operations, maintenance, and engineering departments; and representatives of labor organizations regularly review these reports and share the results of those reviews across all divisions of your organization. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Ft. Totten NTSB report 8/10/10 R-10-17
OHA_000060 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-07-02 | Review the Hazard Identification and Resolution Matrix process in your system safety program plan to ensure that safety-critical systems such as the automatic train control system and its subsystem components are assigned appropriate levels of risk in light of the issues identified in this accident. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Occasional | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | Ft. Totten NTSB report 8/10/10 R-10-18
OHA_000061 | Rail | Rules, Regulations, Procedures | Management of Corrective Action Plans | 2012-02-13 | Develop a formal process by which the general manager and managers responsible for Washington Metropolitan Area Transit Authority operations, maintenance, and engineering will periodically review, in collaboration with the chief safety officer, all safety audits and open corrective action plans, and modify policy, identify and commit resources, and initiate any other action necessary to ensure that the plans are adequately addressed and closed within the required time frame. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2011-04-15 | 2011-04-26 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Ft. Totten NTSB report 8/10/10 R-10-19
OHA_000062 | Rail | Railcar | Crashworthiness | 2012-01-31 | Remove all 1000-series railcars as soon as possible and replace them with cars that have crashworthiness collision protection at least comparable to the 6000 series railcars. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2013-06-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Ft. Totten NTSB report 8/10/10 R-10-20
OHA_000063 | Rail | Railcar | Event Recorders | 2012-01-31 | Ensure that the lead married-pair car set of each train is equipped with an operating onboard event recorder. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Remote | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Ft. Totten NTSB report 8/10/10 R-10-21
OHA_000064 | Rail | Railcar | Event Recorders | 2012-01-31 | Develop and implement a program to monitor the performance of onboard event recorders and ensure they are functioning properly. Safety issue or concern not properly identified, reported, assessed, or mitigated. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Remote | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | Ft. Totten NTSB report 8/10/10 R-10-22
OHA_000065 | Rail | Rules, Regulations, Procedures | Operating and Maintenance Procedures | 2012-01-31 | Lack of definition and documentation criteria for repeat failures, deferred maintenance criteria, prioritization of critical repairs, scheduled maintenance adherence, tracking of open hazards, training policies and standards, preventive maintenance program revisions and approvals, life-cycle planning and management SOPs and methodologies. Safety issue or concern not properly identified, reported, assessed, or mitigated. 9/30/10--These critical processes must be defined and documented. It is recommended that each Maintenance department develop a Maintenance Control Policy to cover these critical areas. Track Maintenance and Structures have provided a curtailed description. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Remote | 2012-12-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1D - Undesirable - Management (ESC) decision | Rail Maint ISA report 9/30/10 M1
OHA_000066 | Rail | Rules, Regulations, Procedures | Operating and Maintenance Procedures - Daily Railcar Inspections | 2012-02-13 | There are no checklists for use in daily inspections of railcars. Potential safety issue results from inadequate or incomplete documentation. 9/30/10--Develop a checklist to be used with the Daily Inspection Procedure. | Potential safety issue results from inadequate or incomplete documentation. | Probable | Marginal | Occasional | 2011-10-31 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 3B - Undesirable - Management (ESC) decision | 4C - Acceptable without review | Rail Maint ISA report 9/30/10 M2
OHA_000067 | Rail | Rules, Regulations, Procedures | Supervisor Duties | 2012-04-18 | Supervisors do not have Standard Operating Procedures or Methodologies for any of their duties; supervisors do not have a formal training program for their position and duties. Potential safety issue results from inadequate or incomplete documentation. 9/30/10--Develop SOPs & methodologies to cover all supervisory duties, including (as applicable) spot checks, prioritization of repairs, field inspections, QA inspections, PPE checks, toolbox meetings and safety contacts, disciplinary processes, on-the-job. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Remote | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M3
OHA_000068 | Rail | Emergency Response | Emergency Preparedness and Security Training | 2012-01-31 | Lack of training for emergency preparedness and security. Inability to respond effectively in a fire/life safety emergency. | Inability to respond effectively in a fire/life safety emergency. | Remote | Catastrophic | Improbable | 2012-12-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M4
OHA_000069 | Rail | Rules, Regulations, Procedures | Continuity of Operations Plan | 2012-04-18 | Lack of procedures to support COOP. Personnel do not properly perform safety related duties. 9/30/10--Develop departmental procedures to support activation of the COOP. | Personnel do not properly perform safety related duties. | Remote | Catastrophic | Remote | 2012-08-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1D - Undesirable - Management (ESC) decision | Rail Maint ISA report 9/30/10 M5
OHA_000070 | Rail | Rules, Regulations, Procedures | Facility Emergency Plans and Procedures | 2012-05-08 | No specific facility emergency plans or procedures. Inability to respond effectively in a fire/life safety emergency. 9/30/10--Develop facility emergency plans and procedures for each facility, to include all-hazards scenarios, including active shooter, weather emergencies, fire, shelter-in-place options, etc. The facility that houses the SAMS departments does have a fac | Inability to respond effectively in a fire/life safety emergency. | Remote | Catastrophic | Occasional | 2012-08-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1C - Unacceptable | Rail Maint ISA report 9/30/10 M6
OHA_000071 | Rail | Rules, Regulations, Procedures | Continuity of Operations Plan | 2012-04-18 | Lack of exercises to test COOP. Personnel do not properly perform safety related duties. 9/30/10--Hold annual exercise to test COOP. | Personnel do not properly perform safety related duties. | Remote | Catastrophic | Improbable | 2012-08-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M7
OHA_000072 | Rail | Rules, Regulations, Procedures | Maintenance Training Programs | 2012-04-18 | There is a lack of certain technical training for maintenance personnel. Personnel do not properly perform safety related duties. 9/30/10--CMNT: Ladders, cranes/ rigging/strapping, PM criticality, defensive driving, small tools COMM: PM criticality, fitness for duty, small tools, lockout/tagout Power: PM criticality ATC: Lone Worker, high voltage, PM criticality TSSM: High voltage, | Personnel do not properly perform safety related duties. | Remote | Catastrophic | Improbable | 2012-03-31 | 2012-03-31 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M8
OHA_000073 | Rail | Rules, Regulations, Procedures | Operating Procedures for GOTRS | 2012-04-17 | No SOP for General Order and Track Right Authorization System (GOTRS). Potential safety issue results from inadequate or incomplete documentation. 9/30/10--Need formal documentation of GOTRS process for meeting to allocate track... | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Remote | 2012-03-31 | 2012-04-17 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M9
OHA_000074 | Rail | Rules, Regulations, Procedures | SOP for Engineering Review Board | 2012-06-28 | No SOP for Engineering Review Board. Potential safety issue results from inadequate or incomplete documentation. 9/30/10--Need formal documentation of ERB process for change control in Maintenance, to ensure the participation of all end users, SAFE and security where appropriate. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Improbable | 2012-06-30 | 2012-06-30 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M10
OHA_000075 | Rail | Management | Staffing | 2012-04-17 | There is no dedicated engineering support for TSSM, COMM, Power, AFC and SAMS, and, as a result, there is a lack of proper engineering support for these areas of Maintenance. Safety issue or concern not properly identified, reported, assessed, or mitigated. 9/30/10--Each maintenance area must have adequate dedicated engineering support. This means that all engineering needs for change control, procedures, training and QA should be met by qualified engineering staff within a reasonable period of time to meet. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Remote | 2012-03-31 | 2012-04-17 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M11
OHA_000076 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-07-02 | No SOPs or procedures in place for Configuration Management & Document Control. Potential safety issue results from inadequate or incomplete documentation. 9/30/10--Ensure that there are formal, documented procedures for configuration management and document control for all maintenance departments, Documentum system is being implemented, but SOPs for its use must be developed for each department. This include | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M12
OHA_000077 | Rail | Rules, Regulations, Procedures | Emergency Preparedness and Security Training | 2012-04-18 | Area emergency response partners have not been trained in the hazards of the facilities to which they may have to respond. This may cause an inability of reponse partners to respond effectively in a fire/life safety emergency. 9/30/10--Include maintenance facilities in emergency responder training. | Inability to respond effectively in a fire/life safety emergency. | Occasional | Catastrophic | Occasional | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | Rail Maint ISA report 9/30/10 M13
OHA_000078 | Rail | Rules, Regulations, Procedures | Refresher Training | 2012-08-06 | No refresher training or retraining program is in place for any courses with the exception of drug and alcohol per FTA requirements and trackwalker recertification. As a result, a safety issue or concern may not be properly identified, reported, assessed, or mitigated. 9/30/10--Perform an analysis with SAFE to determine needed refresher training and retraining requirements, including emergency training. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2012-07-31 | 2012-07-31 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M14
OHA_000079 | Rail | Rules, Regulations, Procedures | CMNT Training Matrix | 2011-09-29 | CMNT has no training matrix. As a result, a potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Develop a matrix that lists training for each position in CMNT, required training and training intervals. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Improbable | 2010-12-31 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Rail Maint ISA report 9/30/10 M15
OHA_000080 | Rail | Rules, Regulations, Procedures | Train-the-Trainer for Maintenance Areas | 2012-02-13 | There is no train the trainer program for Maintenance areas. Since there is a considerable amount of on-the-job training provided in all areas, this is a key omission. This may cause inadequate training of rail personnel. 9/30/10--Review and analyze all OJT, and determine the positions that will require Training skills within the Maintenance function. | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M16
OHA_000081 | Rail | Rules, Regulations, Procedures | Safety Rule Testing Program | 2012-04-17 | There is no formal safety rule testing program in place at WMATA. An indirect hazard may occur due to inadequate or incomplete reporting of unacceptable hazardous conditions. 9/30/10--Develop a formal system-wide process for all levels in all departments to report hazards within the existing rules and procedures structure. | Indirect hazard may occur due to inadequate or incomplete reporting of unacceptable hazardous conditions. | Occasional | Marginal | Remote | 2012-03-31 | 2012-03-31 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M17
OHA_000082 | Rail | Rules, Regulations, Procedures | Maintenance Training Programs | 2012-04-17 | SAFE does not currently review any maintenance training programs. Potential safety issue results from inadequate or incomplete documentation. 9/30/10--Ensure that all training programs are reviewed by safety for compliance with the SSPP and other safety requirements. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Remote | 2012-03-31 | 2012-04-17 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | Rail Maint ISA report 9/30/10 M18
OHA_000083 | Rail | Rules, Regulations, Procedures | SOP for OAPs Review and Revision | 2012-08-06 | There is no SOP for regular review, revision and update of OAPs.This may cause a potential safety issue that results from inadequate or incomplete documentation. 9/30/10--Develop an SOP for the review, revision and update of OAPs, to include the review and approval process with safety review and signoff. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M19
OHA_000084 | Rail | Rules, Regulations, Procedures | Quality Checks of Maintenance Training | 2012-04-17 | QAAW is not currently performing QA on Maintenance training. This could result in inadequate training of rail personnel. 9/30/10--Ensure proper QA is performed on maintenance training programs. | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2012-03-31 | 2012-04-17 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M20
OHA_000085 | Rail | Rules, Regulations, Procedures | Quality Checks of Maintenance Training | 2012-02-13 | There is currently no formal QA performed on trainees in maintenance. This could result in inadequate training of rail personnel. 9/30/10--Ensure a full QA program for evaluation of trainees is developed. | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M21
OHA_000086 | Rail | Rules, Regulations, Procedures | On-the-Job Training for Rail Maintenance | 2012-02-13 | There is currently no formal process or documentation for On-the-Job training for any Maintenance department except for AFC. This could result in inadequate training of rail personnel. 9/30/10--Develop a formal, documented OJT program for all OJT; the AFC format and documentation is an excellent template. | Inadequate training of rail personnel. | Occasional | Negligible | Improbable | 2011-09-30 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Rail Maint ISA report 9/30/10 M22
OHA_000087 | Rail | Rules, Regulations, Procedures | CMNT Contractor Training | 2012-02-13 | There is no formal safety training program in place for contractors working in the CMNT shops. This could result in personnel not properly performing safety related duties. 9/30/10--Develop a formal safety training for contractors and briefing for visitors; ensure all training provided is documented, that visitors are escorted at all times, and that contractors are supervised at all times by CMNT employees. | Personnel do not properly perform safety related duties. | Occasional | Marginal | Improbable | 2011-12-31 | 2011-08-15 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M23
OHA_000088 | Rail | Rules, Regulations, Procedures | Communications and Coordination SOPs | 2012-08-06 | Interdepartmental and interagency communications and coordination are not formally documented. These SOPs must include review of programs and documents as well as formal communications and interactions. This could result in inadequate communication of safety related issues. 9/30/10--Develop SOPs to cover interdepartmental and interagency interactions CMNT: Safety, MTPD, Treasury & Fare collection (to include scheduled delivery of the money trains for maintenance and repair) COMM: Safety, MTPD, ENSS, IRPG Power: Safety, MTPD, | Inadequate communication of safety related issues. | Occasional | Negligible | Remote | 2012-12-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | Rail Maint ISA report 9/30/10 M24
OHA_000089 | Rail | Rules, Regulations, Procedures | Shelf-Life Policies for Materials | 2012-05-31 | There are no formal shelf-life policies in place for materials used in any of the departments audited. This could result in personnel not properly implementing proper safety procedures. 9/30/10--Each department will analyze its materials and develop appropriate shelf-life policies and procedures for perishable items. | Personnel do not implement proper safety procedures. | Occasional | Marginal | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M25
OHA_000090 | Rail | Rules, Regulations, Procedures | Safety Critical Parts, Prcoesses and Systems | 2012-01-31 | Safety-critical parts, processes and systems are not formally identified. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Develop a safety-critical policy and procedures to cover parts, processes and systems in maintenance. This may be included as part of the maintenance policy document. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M26
OHA_000091 | Rail | Rules, Regulations, Procedures | Safety Certification Processes | 2012-04-18 | Departmental participation in safety certification does not occur for all capital acquisitions. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Ensure that SOPS are developed to ensure that IRPG includes end users, safety, MTPD and all appropriate stakeholders per WMATA's safety certification policy and program. In particular, the Sperry Car purchase needs the involvement of SAFE in the | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Remote | 2012-03-31 | 2012-03-31 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M27
OHA_000092 | Rail | Rules, Regulations, Procedures | SOP For Splicing in Emergencies | 2012-07-02 | No SOPs are in place for splicing in emergencies. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Develop SOPs for splicing in emergencies | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Occasional | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 1D - Undesirable - Management (ESC) decision | 3C - Undesirable - Management (ESC) decision | Rail Maint ISA report 9/30/10 M28
OHA_000093 | Rail | Rules, Regulations, Procedures | SOP for Lithium batteries | 2012-07-02 | No SOPs are in place for lithium batteries. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Develop SOPs for lithium batteries | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M29
OHA_000094 | Rail | Rules, Regulations, Procedures | End User Approval Processes | 2012-08-06 | Insufficient participation in end user approval process, vendor QA processes and OEM replacement processes for Power group. This could cause a potential safety issue that results from inadequate or incomplete QA processes and review of OEM replacement. 9/30/10--Ensure that SOPS are developed to ensure that Power is included in all engineering and QA processes applicable to their operation | Potential safety issue results from inadequate or incomplete QA processes and review of OEM replacement. | Remote | Catastrophic | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M30
OHA_000095 | Rail | Rules, Regulations, Procedures | SOP for Incident Debriefings | 2012-08-06 | There are no SOPs in place for departments to participate in critical incident debriefings. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Ensure SOPs are in place to include departments affected by critical incidents in the debriefing process | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Remote | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | Rail Maint ISA report 9/30/10 M31
OHA_000096 | Rail | Rules, Regulations, Procedures | SOP for Emergency Field Notifications | 2012-07-02 | No SOPs in place to ensure field notifications in emergencies are made in remote locations, such as substations. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Ensure SOPs are in place to cover notifications in emergency situations to cover all field assignments without PAs. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Catastrophic | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M32
OHA_000097 | Rail | Rules, Regulations, Procedures | SOP for Vandalism and Graffitti Remediation | 2012-08-06 | No SOPs to cover vandalism or graffiti remediation at Power substations. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Develop SOP to handle graffiti and vandalism at substations | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Remote | 2012-07-31 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | Rail Maint ISA report 9/30/10 M33
OHA_000098 | Rail | Management | Staffing | 2012-04-18 | Understaffing in some departments has led to deferred maintenance and excessive overtime, leading to fatigue. This could cuase safety issues or concerns to go undetected, assessed or mitigated. 9/30/10--Perform manpower analyses for each department in coordination with SAFE. | Inadequate staffing causes safety issue or concern to go undetected, assessed or mitigated. | Remote | Catastrophic | Improbable | 2012-08-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M34
OHA_000099 | Rail | Rules, Regulations, Procedures | SOP for Critical Communications Failures | 2012-02-13 | No SOPs in place for response to critical failures in COMM. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Develop SOPs for response to critical failures | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Critical | Remote | 2011-03-30 |  | Completed | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2D - Undesirable - Management (ESC) decision | Rail Maint ISA report 9/30/10 M35
OHA_0000100 | Rail | Rules, Regulations, Procedures | Communications Contractor Training | 2012-02-13 | Training for contractors working in COMM is inadequate. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Ensure contractors working on property with COMM receive proper ROW safety training, and that the training is properly documented | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2010-12-31 | 2011-08-15 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M36
OHA_0000101 | Rail | Facilities | Communications Rooms | 2012-08-06 | COMM rooms are not maintained in proper and safe order. Several COMM rooms had hazardous conditions. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Ensure that COMM rooms are inspected for safety when entered for work. Violations should be reported, documented and corrected. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M37
OHA_0000102 | Rail | Train Protection System | Advanced Information Management System | 2012-02-13 | Currently, ATC does not have access to the AIMS system, which hinders the diagnostic process. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--The AIMS system must be accessible to all departments performing diagnostic processes for ATC failures and anomalies. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Improbable | 2010-12-31 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Rail Maint ISA report 9/30/10 M38
OHA_0000103 | Rail | Train Protection System | Meggering and Ground Testing Programs | 2012-04-17 | Currently no meggering or ground testing is performed in ATC. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--SOPs for testing of grounds and meggering should be developed and implemented. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2012-03-31 | 2012-03-31 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M39
OHA_0000104 | Rail | Rules, Regulations, Procedures | MSDS Availability to in the field ATC Crews | 2012-08-06 | MSDS are not readily available in the field for ATC crews. This could result in an environmental issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Ensure that ready access to MSDS is available to ATC field technicians | Environmental issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M40
OHA_0000105 | Rail | Rules, Regulations, Procedures | Job Hazard Analyses | 2012-04-17 | Job hazard analyses are not complete for all departments. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Ensure job hazard analyses are completed for all positions | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Remote | 2012-12-30 | 2012-04-17 | Completed | McCoy, Darren | Marginal | 1C - Unacceptable | 3D - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M41
OHA_0000106 | Rail | Management | Material Supplies and Parts Replacement | 2012-04-17 | Critical shortages of materials and replacement parts have resulted from the lack of forward supply points and the inability of departments to purchase and maintain stores. Additionally, the Central supply facility is not open at all the hours the departments have needs, and it closes in bad weather, when crews in the departments it supplies are still working and in need of supplies and parts. This could result in critical materials and replacement parts not being available when needed. 9/30/10--Perform an immediate analysis of the critical supply needs for each department in coordination with SAFE | Critical materials and replacement parts are not available when needed. | Probable | Critical | Occasional | 2012-03-31 | 2012-03-31 | Completed | McCoy, Darren | Critical | 2B - Unacceptable | 2C - Undesirable - Management (ESC) decision | Rail Maint ISA report 9/30/10 M42
OHA_0000107 | Rail | Rules, Regulations, Procedures | Track Replacement Program Plan | 2012-01-31 | Track replacement program plan is not fully documented. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Document the existing work flow plan; recommend adding it to the Maintenance Control Policy | Potential safety issue results from inadequate or incomplete documentation. | Remote | Catastrophic | Improbable | 2012-12-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M43
OHA_0000108 | Rail | Management | Staffing | 2012-06-28 | MOC is not well versed in the events and situation experienced by TSSM. There is no TSSM person at the MOC desk. This could result in inadequate training of MDC personnel. 9/30/10--Training for MOC personnel in prioritization of items for TSSM | Inadequate training of MOC personnel. | Occasional | Marginal | Improbable | 2012-06-30 | 2012-06-30 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M44
OHA_0000109 | Rail | Rules, Regulations, Procedures | SOP for Disposal of Hazardous Waste | 2012-04-17 | Structures has no SOPs for disposal of hazardous waste generated at work sites. This could result in an environmental issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Develop SOPs for hazardous waste for structures | Environmental issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2012-03-31 | 2012-03-31 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M45
OHA_0000110 | Rail | Rules, Regulations, Procedures | Quality Assurance and Auditing of Departments | 2012-02-13 | QA is currently not performing reviews or auditing in any area except CMNT, and is not performing any training audits. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 9/30/10--Ensure all appropriate areas have proper QA support. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Remote | 2011-09-30 | 2011-07-25 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | Rail Maint ISA report 9/30/10 M46
OHA_0000111 | Rail | Rules, Regulations, Procedures | SOP for QA Documentation Annual Review and Revision | 2012-02-13 | No SOP for QA documentation annual review and revision; current documentation is not reviewed by SAFE and does not refer to the SSPP or hazard management functions. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Develop and implement annual review and revision of QA Documentation. Ensure that all QA documentation references the SSPP and hazard management roles and processes and all documentation is reviewed by SAFE. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Improbable | 2011-09-30 |  | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | Rail Maint ISA report 9/30/10 M47
OHA_0000112 | Rail | Rules, Regulations, Procedures | SOP for QA Review of Internal Documentation | 2012-02-13 | No SOP in place for QA's periodic formal review of its internal documentation. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Develop formal SOP for internal controls for QA. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2011-09-30 |  | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Rail Maint ISA report 9/30/10 M48
OHA_0000113 | Rail | Rules, Regulations, Procedures | Training and Certification Program for QAAW Personnel | 2012-02-13 | No training or certification policy or procedures for QAAW staff. This could result in inadequate training of rail personnel. 9/30/10--Develop training and certification policy and procedures for all positions in QAAW. Recommend adding this to existing QA policy document. | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2011-09-30 |  | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M49
OHA_0000114 | Rail | Rules, Regulations, Procedures | Quality Assurance Involvement in Capital Acquisitions | 2012-04-18 | Insufficient involvement of end users and QA in Capital acquisitions. A potential safety issue could result from inadequate or incomplete involvement of end users and QA in Capital acquisitions. 9/30/10--Ensure that end users and QA are involved in all steps of capital acquisitions, including life-cycle planning and programs, & rehabilitation of rolling stock and infrastructure. | Potential safety issue results from inadequate or incomplete involvement of end users and QA in Capital acquisitions. | Occasional | Marginal | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M50
OHA_0000115 | Rail | Rules, Regulations, Procedures | SOP for Safety Contacts | 2012-04-17 | Toolbox meetings and Safety Contacts have worksheets to document them, but no SOPs. A potential safety issue could result from inadequate or incomplete documentation. 9/30/10--Ensure SOPs are developed for Toolbox meetings and Safety Contacts. May be included in Supervisor's Manual/SOPs | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Improbable | 2012-02-29 | 2012-03-31 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | Rail Maint ISA report 9/30/10 M51
OHA_0000116 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 3, Management Structure | 2012-02-13 | The system fail-safe design criteria described in section 3.2 of the SSPP does not account for recent accidents and hazardous conditions. A potential safety issue could result from inadequate or outdated safety documentation. 11/23/10--Note that the SSPP does not contain actual design criteria. The section of the SSPP referenced by TOC's finding is only intended to provide a system description. Final revised SSPP to be provided to TOC by January 1, 2011. | Inadequate or outdated safety documentation. | Improbable | Negligible | Improbable | 2011-01-01 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 4E - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000117 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 3, Management Structure | 2012-02-13 | The system fail-safe design criteria described in section 3.2 of the SSPP does not account for recent accidents and hazardous conditions. A potential safety issue could result from inadequate or ioutdated documentation. | Inadequate or outdated safety documentation. | Improbable | Negligible | Improbable | 2011-03-15 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4E - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000118 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 3, Management Structure | 2012-02-13 | SAFE (System Safety and Environmental Management) organizational responsibilities are not clearly defined. A potential safety issue could result from inadequate or outdated safety and environmental responsibilities. | Inadequate or outdated safety and environmental responsibilities. | Improbable | Negligible | Improbable | 2011-03-15 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4E - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000119 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 3, Management Structure | 2012-02-13 | Responsibilities of the CSO (Chief Safety Officer) appear to be misstated in the SSPP. A potential safety issue could result from inadequate or outdated safety responsibilities. | Inadequate or outdated safety responsibilities. | Improbable | Negligible | Improbable | 2011-03-15 | 2011-03-15 | Completed | McCoy, Darren | Critical | 4E - Acceptable without review | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000120 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 4, Plan Review and Modification | 2012-02-13 | The SSPP was not updated in response to prior TOC comments or the last Triennial Review. A potential safety issue could result from inadequate or incomplete documentation. 11/23/10--SSPP is being updated to reflect TOC, FTA and WMATA SAFE findings and recommendations. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Improbable | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000121 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 4, Plan Review and Modification | 2012-02-13 | Non-SAFE departments and the ELT (Executive Leadership Team) are not engaged in updates to the SSPP. This could result in personnel failing to implement proper safety proceddures. 11/22/10-- SAFE has involved appropriate non-SAFE departments, including WMATA's Executive Leadership Team in the review and revision of the SSPP. Signature page will include sign-off from WMATA departmental leadership to provide TOC with verification tha | Personnel do not implement proper safety procedures. | Occasional | Marginal | Improbable | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000122 | Rail | Rules, Regulations, Procedures | Executive Safety Committee Policy Instruction | 2012-02-13 | The SSEC policy/instruction is not being implemented. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE to revise P/I 10.2/1 to document the new Executive Safety Committee structure, roles and responsibilities. The revised policy instruction will be provided to TOC for review once complete. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2011-08-31 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000123 | Rail | Rules, Regulations, Procedures | Corrective Action Plan Definition | 2012-02-13 | Corrective action plan (CAP) definition and implementation do not comply with TOC requirements. This could result in personnel failing to implement proper safety procedures. 11/23/10--SAFE will revise the SSPP to define the corrective action plan process and to ensure this process is compliant with the requirements of TOC's Program Standards and Procedures. WMATA will continue to make every effort to develop and submit CAPs i | Personnel do not implement proper safety procedures. | Occasional | Marginal | Improbable | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000124 | Rail | Rules, Regulations, Procedures | Safety Related Procedures | 2012-02-13 | Safety policies, procedures, and plans are outdated and inadequately documented. This could result in personnel failing to implement proper safety procedures. 11/23/10--SAFE to review all current safety plans, policies and procedures and make revisions as necessary. SAFE will post revised safety plans, policies and procedures to the intranet. TOC will be provided access to the intranet to verify that revised d | Personnel do not implement proper safety procedures. | Probable | Marginal | Improbable | 2012-01-31 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 3B - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000125 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 5, SSPP Implementation | 2012-02-13 | SAFE capabilities, responsibilities, and procedures are not fully established. This could result in personnel failing to implement proper safety procedures. 11/23/10--SAFE conducted a resource assessment of the Safety Department between June and July, 2010. A summary of the assessment results was presented to the ESC on August 24, 2010, which TOC attended. A copy of the final resource assessment report was p | Personnel do not implement proper safety procedures. | Remote | Catastrophic | Improbable | 2010-11-22 | 2011-03-16 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000126 | Rail | Rules, Regulations, Procedures | WMATA Design Criteria Updates | 2012-02-13 | WMATA Design Criteria updates are incomplete. As a result, current safety or security related design criteria may not be incorporated into equipment or system specifications. 11/23/10--CENI will meet with MPTD to discuss needs assessment and technology to enhance security measures as well as physical hardening. CENI will update the security design manual in coordination with the needs assessment. | Current safety or security related design criteria is not being incorporated into equipment or system specifications. | Remote | Catastrophic | Improbable | 2011-10-31 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000127 | Rail | Rules, Regulations, Procedures | Quality Assurance Policy and Procedures Manual | 2012-08-06 | The WMATA Quality Assurance Policy and Procedures Manual is outdated. This could result in personnel failing to implement proper safety procedures. 11/23/10--SAFE to review and revise the Office of Quality Assurance Policy and Procedures Manual to reflect WMATA's current organization and practices. The revised QA Policy and Procedures Manual will be provided to TOC once complete. | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000128 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-02-13 | The WMATA Hazard management process does not meet TOC requirements. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. SAFE is also developing a new hazard management procedure to implement this process. The final revised SSPP will be provided to TOC by January 1, 2011. The new Hazard Ma | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 1C - Unacceptable | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000129 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-02-13 | WMATA has not met requirements for TOC notification of unacceptable hazardous conditions. An indirect hazard may occur due to inadequate or incomplete reporting of unacceptable hazardous conditions. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. SAFE is also developing a new hazard management procedure to implement this process. The final revised SSPP will be provided to TOC by January 1, 2011. The new Hazard Ma | Indirect hazard may occur due to inadequate or incomplete reporting of unacceptable hazardous conditions. | Occasional | Marginal | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000130 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-02-13 | The WMATA process of hazard investigation is unclear. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. SAFE is also developing a new hazard management procedure to implement this process. The final revised SSPP will be provided to TOC by January 1, 2011. The new Hazard Ma | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000131 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-08-06 | HIRM (Hazard Identification and Resolution Matrix) items remain open. Identified safety issues and concerns are not properly mitigated. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. SAFE is also developing a new hazard management procedure to implement this process. The final revised SSPP will be provided to TOC by January 1, 2011. The new Hazard Ma | Safety issue or concern identified by not mitigated. | Occasional | Catastrophic | Occasional | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | 2010 Triennial Report
OHA_0000132 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-08-06 | Environmental issues are not addressed or included in hazard management. This could result in a environmental issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE is developing a Safety Measurement IT System that will incorporate hazard program information collected from multiple sources including the IH Tracking Matrix. TOC will be allowed to review this System once it is fully operational to verify | Environmental issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000133 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-02-13 | The SSPP Element 6 is outdated. This could result in personnel not implementing proper safety procedures. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. The final revised SSPP will be provided to TOC by January 1, 2011. | Personnel do not implement proper safety procedures. | Occasional | Marginal | Improbable | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000134 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program; | 2012-02-13 | The Hazard Management Procedure is insufficient to meet existing needs. As a result, personnel may not implement proper safety procedures. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. SAFE is also developing a new hazard management procedure to implement this process. The final revised SSPP will be provided to TOC by January 1, 2011. The new Hazard Ma | Personnel do not implement proper safety procedures. | Occasional | Catastrophic | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Catastrophic | 1C - Unacceptable | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000135 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-02-13 | Too few sources provide input regarding hazardous conditions. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. SAFE is also developing a new hazard management procedure to implement this process. The final revised SSPP will be provided to TOC by January 1, 2011. The new Hazard Ma | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Catastrophic | 1C - Unacceptable | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000136 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program; Hazard Management Procedure | 2012-02-13 | No CAP process for hazardous conditions currently exists. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. SAFE is also developing a new hazard management procedure to implement this process. The final revised SSPP will be provided to TOC by January 1, 2011. The new Hazard Ma | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Catastrophic | 1C - Unacceptable | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000137 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-02-13 | The SSEC role in hazard management is too limited. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE will revise P/I 10.2/1 to document the new Executive Safety Committee structure, roles and responsibilities. The revised policy instruction will be provided to TOC for review once complete. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000138 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-02-13 | Hazard management does not include smaller incidents. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE has updated the SSPP to document its new hazard management process. SAFE is also developing a new hazard management procedure to implement this process. The final revised SSPP will be provided to TOC by January 1, 2011. The new Hazard Ma | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Critical | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Catastrophic | 2D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000139 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-05-22 | The role of Procedure 2.2/1 is unclear. A potential safety issue may result from inadequate or incomplete documentation. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Improbable | 2012-05-31 | 2012-05-31 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000140 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 8, Managing Safety in System Modifications | 2012-02-13 | The SSPP does not verify the governing WMATA procedures for managing safety in system modifications. As a result, personnel may not implement proper safety procedures. 11/23/10--SAFE will revise the SSPP to reflect the most current policies for system modifications. The final revised SSPP to be provided to TOC for review by January 1, 2011. | Personnel do not implement proper safety procedures. | Remote | Catastrophic | Improbable | 2011-01-01 | 2011-05-17 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000141 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 9, Safety Data Acquisition and Analysis | 2012-02-13 | SSPP Element 9 does not reflect current WMATA practice on safety data acquisition and analysis. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE will revise the SSPP to reflect current WMATA practice for safety data acquisition and analysis. The final revised SSPP to be provided to TOC for review by January 1, 2011. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000142 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 9, Safety Data Acquisition and Analysis | 2012-08-06 | No rules and procedures to guide safety data collection and analysis are in place. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE will revise Section 9.0 of the SSPP to establish rules to guide safety data collection and analysis, including implementation and use of the new Safety Measurement IT System. Final revised SSPP to be provided to TOC by January 1, 2011. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000143 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 9, Safety Data Acquisition and Analysis | 2012-08-06 | Integration and analysis of safety data is disjointed and no assurance of NTD/SSO consistency is provided. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE will revise Section 9.0 of the SSPP to establish rules to guide safety data collection and analysis, including implementation and use of the new Safety Measurement IT System. Final revised SSPP to be provided to TOC by January 1, 2011. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000144 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 9, Safety Data Acquisition and Analysis | 2012-08-06 | Sources of safety data input and analysis are limited. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SAFE will revise Section 9.0 of the SSPP to establish rules to guide safety data collection and analysis, including implementation and use of the new Safety Measurement IT System. Final revised SSPP to be provided to TOC by January 1, 2011. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000145 | Rail | Rules, Regulations, Procedures | Accident Investigation Procedure | 2012-02-13 | WMATA is out of compliance with TOC accident/incident investigation requirements. As a result, personnel may not implement proper safety related procedures. 11/23/10--Written recovery plan developed and submitted to TOC. TOC approval of the plan was received August 19, 2010. WMATA to complete future accident investigations in accordance with TOC schedule and content requirements. | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2010-08-19 | 2010-11-23 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000146 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 6, Hazard Management Program | 2012-02-13 | The CAP process at WMATA does not comply with TOC requirements. As a result, personnel may not implement proper safety related procedures. 11/23/10--SAFE will revise the SSPP to address this finding. SAFE will also develop a new hazard management procedure to implement the new hazard management procedure. The final revised SSPP to be provided to TOC for review by January 1, 2011. The new h | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000147 | Rail | Rules, Regulations, Procedures | Accident Investigation Procedure | 2012-02-13 | WMATA accident/incident investigation procedures are unclear. As a result, personnel may not implement proper safety related procedures. 11/23/10--SAFE will revise the Accident Investigation Procedures and SSPP to address this finding. Final revised SSPP to be provided to TOC for review by January 1, 2011. Revised Accident Investigation Procedures to be provided to TOC by TBD. | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2011-08-31 |  | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000148 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 11, Emergency Management | 2012-04-19 | WMATA is not in compliance with TOC Program Standard & Procedure section 7.1- Drills and Exercises. As a result, personnel may not implement proper safety related procedures. OEM to develop schedule of emergency drills on an annual basis. MTPD will incorporate all findings/lessons learned through emergency drills into the security CAP tracking log developed in response to Deficiency SEC 1-2 as noted above. OEM will provide TOC | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2011-09-30 | 2011-09-30 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000149 | Rail | Rules, Regulations, Procedures | MTPD OEM Staff Deployment to the OCC Policy | 2012-04-19 | The MTPD OEM (Office of Emergency Management Division) currently deploys one fire/life/safety coordination officer to the Operations Control Center (OCC) during the daily am/pm rush hours; deployment of additional personnel may be warranted. As a result WMATA is unable to effectively respond during a fire/life safety emergency. Current staffing of OEM staff during rush hour is a voluntary activity designed to enhance response and relay information quickly. OEM has evaluated the assignment of additional staff during non-peak hours and has determined that it does not have suffici | Inability to respond effectively in a fire/life safety emergency. | Remote | Marginal | Improbable | 2011-04-30 | 2011-04-30 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000150 | Rail | Rules, Regulations, Procedures | Incident Command System and National Incident Management System Plans and Procedures | 2012-04-19 | WMATA is currently using incident management terms, plans and procedures that do not comply with the Incident Command System (ICS) and National Incident Management System (NIMS). As a result, personnel may not implement proper safety related procedures. General Order #364 - Incident Command System is being revised to comply with NIMS and ICS | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2011-08-31 | 2011-08-31 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000151 | Rail | Rules, Regulations, Procedures | Internal Safety Auditing Procedure | 2012-02-13 | The applicable ISA (Internal Safety Audits) procedure at WMATA contains inaccurate information. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--ISA Recovery Plan was developed and implemented. ISA procedure was also revised. TOC approved ISA Procedure on August 15, 2010 and the ISA Recovery Plan on August 19, 2010. SSPP has been revised to reflect most current ISA procedure. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2011-03-31 | 2011-06-28 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000152 | Rail | Rules, Regulations, Procedures | Internal Safety Auditing Procedure | 2012-02-13 | ISAs have not been performed in accordance with the schedule and procedures. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--ISA Recovery Plan was developed and implemented. Approval letter was received from TOC on August 19, 2010. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2010-08-19 | 2010-11-23 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000153 | Rail | Rules, Regulations, Procedures | Internal Safety Auditing Procedure | 2012-02-13 | The WMATA GM Annual Certification Letters do not specify areas of non-compliance with the SSPP/SEPP, in accordance with TOC requirements. A potential safety issue could result from inadequate or incomplete documentation. 11/23/10--SAFE has evaluated this finding using a hazard analysis approach and has determined that it does not present a hazard or threat to the system. Given the negligible safety nature of this finding, WMATA requests that it be closed at this time. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Improbable | 2011-02-01 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000154 | Rail | Rules, Regulations, Procedures | Internal Safety Auditing Procedure | 2012-02-13 | The role of WMATA auditor general in ISAs is not clear. As a result, personnel may not implement proper safety related procedures. 11/23/10--SAFE will revise SSPP to address this finding. Final revised SSPP to be provided to TOC for review by January 1, 2011. | Personnel do not implement proper safety related procedures. | Remote | Marginal | Improbable | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000155 | Rail | Rules, Regulations, Procedures | Internal Safety Auditing Procedure | 2012-02-13 | Many recent internal audits were not performed by WMATA staff. If audits are performed by unqualified external staff, a safety issue or concern could result. 11/23/10--SAFE has evaluated this finding using a hazard analysis approach and has determined that it does not present a hazard or threat to the system. WMATA has developed and is implementing a new Internal Safety Audit Procedure. At this time no federa | Audit performed by unqualified external staff leads to safety issue or concern. | Occasional | Negligible | Improbable | 2011-06-30 | 2011-05-17 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000156 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 13, Rules and Procedures Compliance | 2012-02-13 | Section 13 of the WMATA SSPP states that the MSRPH (Metrorail Safety Rules and Procedures Handbook) shall be revised every two years, but this has not been WMATA practice. As a result, personnel may not implement proper safety related procedures. 11/23/10--SAFE to revise SSPP to reflect the current rules and procedures review and update process. Final revised SSPP to be provided to TOC by January 1, 2011. | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2011-01-01 | 2011-05-17 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000157 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 13, Rules and Procedures Compliance | 2012-02-13 | Section 13 of the WMATA SSPP does not describe current practice in rule compliance and enforcement activities. As a result, personnel may not implement proper safety related procedures. 11/23/10--SAFE has evaluated this finding using a hazard analysis approach and has determined that it does not present a hazard or threat to the system. Given the negligible safety nature of this finding, WMATA requests that it be closed at this time. | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Remote | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000158 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 13, Rules and Procedures Compliance | 2012-02-13 | The safety department does not analyze rule compliance issues through the hazard management process, as specified in SSPP Section 13.4. As a result, personnel may not implement proper safety related procedures. 11/23/10--SAFE will develop a procedure to specify how SAFE will work with other WMATA departments to collect and manage rule compliance data for integration into the hazard management process. This procedure will be provided to TOC once developed (by Jun | Personnel do not implement proper safety related procedures. | Occasional | Catastrophic | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Catastrophic | 1C - Unacceptable | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000159 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 13, Rules and Procedures Compliance | 2012-02-13 | There does not appear to be a structured program for rules and procedures checks in the WMATA OCC/MOC. As a result, personnel may not implement proper safety related procedures. 11/23/10--SAFE to develop a rule check procedure to address TOC findings. In addition, the Assistant Superintendents of ROCC/MOC are developing a QA type of check list to be used to ensure that all ROCC/MOC personnel have a full understanding of all rul | Personnel do not implement proper safety related procedures. | Probable | Catastrophic | Improbable | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Catastrophic | 1B - Unacceptable | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000160 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 4, Plan Review and Modification | 2012-02-13 | Not all OCC personnel appear to be completely familiar with the WMATA SSPP. As a result, personnel may not properly perform safety related duties. 11/23/10--SAFE has evaluated this finding using a hazard analysis approach and has determined that it does not present a hazard or threat to the system. Given the negligible safety nature of this finding, WMATA requests that it be closed at this time. | Personnel do not properly perform safety related duties. | Probable | Negligible | Improbable | 2011-06-30 | 2011-07-19 | Completed | McCoy, Darren | Negligible | 4B - Acceptable with ESC review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000161 | Rail | Comms. | System-Wide Radio Coverage | 2012-02-13 | WMATA OCC supervisors and communications personnel do not appear to follow a precise process for identifying areas of potentially poor radio coverage. Delayed communication could result during an emergency event due to potentially poor radio coverage. 11/23/10--Areas that have poor radio communication are being identified and a MAXIMO incident is being created. This should help correct the identified issues until the new radio system is placed on line. | Delayed communication in the event of an emergency due to potentially poor radio coverage. | Remote | Catastrophic | Remote | 2011-08-31 |  | Completed | McCoy, Darren | Marginal | 1D - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | 2010 Triennial Report
OHA_0000162 | Rail | Rules, Regulations, Procedures | SOP for OCC and MOC in-fied Requirements | 2012-02-13 | There is no formal plan, policy, or procedure that requires OCC and MOC personnel to spend time in the field on a regular basis. As a result, OCC/MOC personnel could become unfamiliar with daily field operations. 11/23/10--The shortage of manpower has prevented regular field visits from taking place on regular bases. However, now that we have six (6) Assistant Superintendents trained ROCC will begin a regular field visit schedule. Once we have hired and trained ad | OCC / MOC personnel unfamiliar with daily field operations. | Probable | Marginal | Remote | 2011-06-30 | 2011-06-14 | Completed | McCoy, Darren | Marginal | 3B - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | 2010 Triennial Report
OHA_0000163 | Rail | Rules, Regulations, Procedures | Blackberry Rule Compliance Program | 2012-02-13 | The WMATA Blackberry rule compliance program lacks a formal written plan, policy, or procedure guiding its implementation. Personnel fail to follow proper rules and procedures. 11/23/10--SAFE is developing a Rule Check/Compliance Procedure in response to this and its own internal safety audit findings. | Personnel fail to follow proper rules and procedures. | Occasional | Negligible | Remote | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000164 | Rail | Rules, Regulations, Procedures | SOP for Performance Tracking Management System | 2012-04-18 | The performance tracking management system lacks a formal written plan, policy, or procedure guiding its implementation. Personnel fail to follow proper rules and procedures. | Personnel do not properly perform safety related duties. | Occasional | Negligible | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000165 | Rail | Rules, Regulations, Procedures | QAAW Procedure for Addressing Safety-Critical Issues | 2012-02-01 | At the time of the review, QAAW (Quality Assurance and Warranty) did not appear to have a formal process or procedure for reporting or addressing hazards or safety-critical issues found during quality audits in coordination with SAFE. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--To be addressed in SSPP revision and new hazard management procedure. WMATA SAFE is updating the SSPP and is developing a new hazard management procedure. Final revised SSPP to be provided to TOC by January 1, 2011. New hazard management proce | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2011-09-30 | 2011-10-19 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000166 | Rail | Management | Field Supervisor Staffing Levels | 2012-02-13 | Field supervisor staffing levels may not be appropriately distributed among the divisions. Inadequate staff could cause a safety issue or concern to go undetected, assessed, or mitigated. 11/23/10--RTRA to evaluate system-wide field supervisor staffing levels by April 2011. | Inadequate staffing causes safety issue or concern to go undetected, assessed or mitigated. | Occasional | Marginal | Improbable | 2011-04-30 | 2011-09-20 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000167 | Rail | Rules, Regulations, Procedures | Track Safety Rules | 2012-02-13 | The TOC review team observed several ROW safety rule violations by personnel working on or near the ROW. Personnel could be exposed to unsafe condictions due to violations of ROW safety rules. 11/23/10--Evaluate the resources available to conduct required training programs to ensure that all training requirements will be completed. Provide the completed evaluation to TOC. Complete the implementation of the new ROW safety program and associated | Personnel exposed to unsafe conditions due to violations of ROW safely rules. | Probable | Catastrophic | Improbable | 2012-01-31 | 2011-05-17 | Completed | McCoy, Darren | Catastrophic | 1B - Unacceptable | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000168 | Rail | Rules, Regulations, Procedures | Station Preventive Mainteannce Practices | 2012-02-13 | Current preventive maintenance practice for stations does not appear sufficient to address numerous issues observed by the review team. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--TRST Structural Engineer will work with PLNT and other offices to evaluate current preventive maintenance practices per industry standards. TRST will provide TOC with a memo stating if any changes were made to the current preventive maintenance. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2011-08-31 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000169 | Rail | Rules, Regulations, Procedures | Elevator Preventive Maintenance Practices | 2012-05-01 | Elevator preventive maintenance compliance for April 2010 (latest month available) was 63.7 percent. This could result in elevators not being available in the event of an emergency - particularly at the Forest Glenn Station. 11/23/10--AGM TIES to devise and implement a written plan to achieve compliance with preventive maintenance procedures for elevators and escalators. | Elevators not available in the event of an emergency - particularly at Forest Glen Station. | Occasional | Catastrophic | Occasional | 2012-04-30 | 2012-04-30 | Completed | McCoy, Darren | Critical | 1C - Unacceptable | 2C - Undesirable - Management (ESC) decision | 2010 Triennial Report
OHA_0000170 | Rail | Rules, Regulations, Procedures | Escalator Preventive Maintenance Practices | 2012-05-01 | Escalator preventive maintenance compliance for April 2010 (latest month available) was 56.1 percent. This could result in inoperable escalators being used as stairs. 11/23/10--AGM TIES to devise and implement a written plan to achieve compliance with preventive maintenance procedures for elevators and escalators. | Inoperable escalators being used as stairs. | Frequent | Critical | Occasional | 2012-04-30 | 2012-04-30 | Completed | McCoy, Darren | Critical | 2A - Unacceptable | 2C - Undesirable - Management (ESC) decision | 2010 Triennial Report
OHA_0000171 | Rail | Comms. | Comprehensive Radio Control System | 2012-02-13 | Comprehensive Radio Control System (CRCS) radios have not been provided to ELES (Elevator Escalator). As a result these individuals may have no means of radio communication. 11/23/10--AGM Ties to devise and implement a written CRCS system improvement plan. | No radio communication. | Occasional | Critical | Improbable | 2011-06-30 |  | Completed | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000172 | Rail | Rules, Regulations, Procedures | Station Preventive Mainteannce Practices | 2012-02-13 | Current preventive maintenance practices do not appear sufficient to fully address alkaline aggregate reaction issues observed by the review team. This could cause tripping hazards in passenger areas. 11/23/10--TRST will provide a copy of the Alkaline Aggregate Reaction Report and IRD6 program. TRST engineering will review current preventive maintenance practices to see if they are adequate to fully address alkaline aggregate reaction issues and will | Tripping hazards in passenger areas. | Probable | Critical | Improbable | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 2B - Unacceptable | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000173 | Rail | Rules, Regulations, Procedures | Station Preventive Mainteannce Practices | 2012-02-13 | Current preventive maintenance practices do not appear sufficient to fully address concrete spalls with exposed rebar issues observed by the review team. This could cause tripping hazards in passenger areas. 11/23/10--TRST will provide a copy of the Alkaline Aggregate Reaction Report and IRD6 program. TRST engineering will review current preventive maintenance practices to see if they are adequate to fully address alkaline aggregate reaction issues and will | Tripping hazards in passenger areas. | Occasional | Critical | Improbable | 2011-08-31 | 2011-08-15 | Completed | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000174 | Rail | Rules, Regulations, Procedures | Bridge and Structures Preventive Mainteannce Practices | 2012-02-13 | Current preventive maintenance practices do not appear sufficient to fully address missing bolts on bridge structures and cracked column footings observed by the review team. This could cause a failure of bridge structures. 11/23/10--TRST will provide a copy of the Alkaline Aggregate Reaction Report and IRD6 program. TRST engineering will review current preventive maintenance practices to see if they are adequate to fully address alkaline aggregate reaction issues and will | Failure of bridge structures. | Occasional | Catastrophic | Improbable | 2011-08-31 | 2011-08-15 | Completed | McCoy, Darren | Catastrophic | 1C - Unacceptable | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000175 | Rail | Rules, Regulations, Procedures | Bridge and Structures Preventive Mainteannce Practices | 2012-02-13 | Current preventive maintenance practices do not appear sufficient to fully address delaminated and exposed concrete encasement beams. Fallen debris could cause a tripping hazard in passenger areas. 11/23/10--TRST will provide a copy of the Alkaline Aggregate Reaction Report and IRD6 program. TRST engineering will review current preventive maintenance practices to see if they are adequate to fully address alkaline aggregate reaction issues and will | Debris causing tripping hazards in passenger areas. | Occasional | Critical | Improbable | 2011-08-31 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 2C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000176 | Rail | Rules, Regulations, Procedures | Construction Safety and Environmental | 2012-02-13 | Construction projects that take place adjacent to WMATA facilities may pose potential safety issues, but WMATA does not have a formal written plan, policy, or procedure in place to monitor and control such projects. A WMATA employee or passenger could be exposed to construction hazards. 11/23/10--CENI will provide the Adjacent Construction Procedures Manual. CENI will review the manual for conformance to requirements, including safety and processes to insure WMATA facilities are not being compromised. | WMATA employee or passenger exposure to construction hazards. | Occasional | Critical | Improbable | 2011-08-31 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 2C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000177 | Rail | Rules, Regulations, Procedures | Bridge and Structures Preventive Mainteannce Practices | 2012-02-13 | Current preventive maintenance practices do not appear sufficient to fully address seismic evaluations. TRST Structural Engineer will evaluate current preventive maintenance practices of seismic evaluations and water intrusion and will provide a copy of the findings to TOC. | Seismic event. | Remote | Catastrophic | Improbable | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000178 | Rail | Rules, Regulations, Procedures | Bridge and Structures Preventive Mainteannce Practices | 2012-02-13 | Current preventive maintenance practices do not appear sufficient to fully address water intrusion issues observed by the review team. 11/23/10--TRST Structural Engineer will evaluate current preventive maintenance practices of seismic evaluations and water intrusion and will provide a copy of the findings to TOC. | Slippery surfaces. | Occasional | Critical | Improbable | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 2C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000179 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-02-13 | WMATA lacks quick and easy access to critical documents. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--CENI has engaged two consultants to update drawings to CAD files. Drawings will be put on Documentum when completed | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2013-01-31 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000180 | Rail | Facilities | Box Structures | 2012-02-13 | With respect to enclosed box structures, inspectors may face unsafe conditions or have no access to complete inspections of internal areas. This could cause an inability of inspectors to inspect critical areas. 11/23/10--TRST will provide a written procedure on what to do when enclosed box structures are inaccessible and will provide TOC with the new procedure upon completion. | Inability to inspect critical areas. | Occasional | Marginal | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000181 | Rail | Rules, Regulations, Procedures | WMATA Structural Inspection Standard Procedure | 2012-02-13 | At the time of the review, the new WMATA Structural Inspection Standard Procedure was still under development. As a result, personnel may not implement proper safety related procedures. 11/23/10--TRST will complete and submit to TOC the new WMATA Structural Inspection Standard Procedure when completed. The document will undergo a peer review by GEC consultants. In addition, to better manage these efforts the CENI will reorganize with Dep | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Improbable | 2011-06-30 | 2011-06-13 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000182 | Rail | Rules, Regulations, Procedures | WMATA Structural Inspection Standard Checklists | 2012-02-13 | WMATA did not use a structural inspection checklist for inspectors to perform their duties. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--Checklist will be developed prior to completion of the Structural Inspection Manual. This will allow for immediate deployment of the checklist. The manual will then include all “check” procedures which may be valid for inspections. | Not following / checking procedures - Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Critical | Improbable | 2011-06-30 | 2011-03-15 | Completed | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000183 | Rail | Rules, Regulations, Procedures | WMATA Structural Inspection Scale | 2012-02-13 | It appears that the FHWA rating scale (0 to 9) is not fully defined or understood by inspectors. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--TRST will evaluate understanding of FHWA rating scale with structural inspectors and based on findings will develop refresher training. TRST will submit a summary of the findings and refresher training curriculum to TOC when complete. CENI wil | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Negligible | Improbable | 2011-03-31 | 2011-06-13 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000184 | Rail | Rules, Regulations, Procedures | Corrective Action Plan Implementation | 2012-02-13 | There is not a formal follow-up process that ensures deficiencies are corrected by outside departments in a timely manner. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--TRST to evaluate the best location for positive locking bars at each exit point and to develop a formal plan to address the condition of emergency exit signs and for tracking all other critical items related to emergency exits and emergency exit | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Improbable | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 1C - Unacceptable | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000185 | Rail | Facilities | Emergency Exit Signage | 2012-02-13 | Some emergency exit signage is unclear due to various reasons, including caked-on grime, age, “wear and tear,” and/or insufficient lighting. This could an inadequate or unclear emergency egress path. 11/23/10--TRST will reinstruct inspectors of current procedures for inspecting emergency exit signage. Reinstruction will include documenting TRST responsibilities and following those to closure and will include procedures for submitting Maximo tickets f | Inadequate or unclear emergency egress path. | Probable | Catastrophic | Improbable | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 1B - Unacceptable | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000186 | Rail | Facilities | Hatch Door Positive Locking Bars | 2012-02-13 | The field visits indicated that hatch door “positive locking bars” are not always easy to locate. This could cause an inability to open hatch doors. 11/23/10--AGM TIES to evaluate the best location for positive locking bars at each exit point and to develop a formal plan to address the condition of emergency exit signs and for tracking all other critical items related to emergency exits and emergency | Inability to open hatch doors. | Probable | Catastrophic | Improbable | 2011-07-31 | 2011-07-19 | Completed | McCoy, Darren | Negligible | 1B - Unacceptable | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000187 | Rail | Management | Staffing | 2012-04-18 | Safety-related inspections were found to be performed on-time; however, there is not a plan in place to assess staffing needs in light of future line expansions. Inadequate staffing could cause a safety issue or concern to go undetected, assessed, or mitigated. 11/23/10--AGM TIES to evaluate if additional inspection staff will be required to support the Dulles extension. Organizational staffing needs are evaluated on an ongoing basis as a matter of standard management practice. | Inadequate staffing causes safety issue or concern to go undetected, assessed or mitigated. | Occasional | Marginal | Remote | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | 2010 Triennial Report
OHA_0000188 | Rail | Rules, Regulations, Procedures | 490 MHz Radio System Training | 2012-07-02 | Many Communications Technicians have not received classroom training on the 490 MHz radio system. This could result in an inability to operate the 490Mhz radio system. 11/23/10--WMATA Status Summarized: • The COMM Radio Instructor has identified that the original vendor training was presented in approximately 14 modules, each generally 1 to 2 days in length. • The COMM Radio Instructor has been supplied with the vendor | Inability to operate 490Mhz radio system | Occasional | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000189 | Rail | Rules, Regulations, Procedures | MAXIMO | 2012-08-06 | Communications lacks MAXIMO capabilities in the areas of system availability and worst performing units, among others. Inadequate staffing could cause a safety issue or concern to go undetected, assessed, or mitigated. 11/23/10--IT Maximo personnel will work to define a process that will provide reports on worst performing communications units. Based upon current staffing levels within the Communications Branch, it is not possible to provide a position with time dedica | Inadequate staffing causes safety issue or concern to go undetected, assessed or mitigated. | Occasional | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000190 | Rail | Management | Staffing | 2012-02-13 | Communications appears to lack engineering support in areas such as trouble support, PMI development, and EMI development. This could result in inoperable communications equipment. 11/23/10--CENI will reorganize with Deputy Chief positions specific to disciplines, including Communications/Network Systems. This provides more interaction with maintenance and the reorganization provides intentional interface through designated maintena | Inoperable communication equipment. | Occasional | Critical | Improbable | 2011-03-31 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 2C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000191 | Rail | Management | Comms Staffing | 2012-02-13 | Communications does not appear to be sufficiently involved in project design and implementation. An indirect hazard may occur due to inadequate collaboration between project design and the Communications Department. 11/23/10--CENI has established regular meetings between engineering and maintenance, as indicated by the recent Narrow Banding requirements. The CENI will reorganize with Deputy Chief positions specific to disciplines, including Communications/Network Sys | Indirect hazard may occur due to inadequate collaboration between project design and Communications Department. | Occasional | Marginal | Improbable | 2011-03-31 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000192 | Rail | Rules, Regulations, Procedures | Volt Metter Calibration | 2012-06-28 | The review team observed volt meters with expired calibration. This could cause an inability to accurately determine system operation within required parameters. 11/23/10--AGM TIES to develop a procedure for calibration and use of precision measurement and testing equipment. Procedure to be provided to TOC once complete. | Inability to accurately determine system operation within required parameters. | Remote | Critical | Improbable | 2012-06-30 | 2012-06-30 | Completed | McCoy, Darren | Marginal | 2D - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000193 | Rail | Rules, Regulations, Procedures | Brake Disc Dishing Measurement | 2012-04-18 | Brake disc dishing was observed to be measured with a non-precision tool in violation of WMATA procedure. This could result in a brake failure of one truck. 11/23/10--AGM TIES to develop a procedure for calibration and use of precision measurement and testing equipment. Procedure to be provided to TOC once complete. | Brake failure on one truck. | Remote | Marginal | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000194 | Rail | Rules, Regulations, Procedures | Preventive Maintenance Documentation | 2012-02-13 | Although WMATA is in the process of incorporating its Preventive Maintenance Inspections (PMI) information into MAXIMO, several audited (hard copy) data sheets for PMIs were not signed off by the technician and a supervisor. As a result, personnel may not implement proper safety related procedures. 11/23/10--ATC has adopted the Code of Federal Regulations Title § 236.110, “Results of Tests” and Code of Federal Regulations Title § 236.917, “Retention of Records.” 1. Results of tests that pertain to installation or modification must be retained for | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Improbable | 2011-03-31 | 2011-06-14 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000195 | Rail | Rules, Regulations, Procedures | ATC Preventive Maintenance | 2012-04-17 | The index list for ATC (Automatic Train Control) PMIs has errors in frequency and dates of revision. Also, PMIs do not incorporate a PMI number, description, date, and revision number on each page. As a result, personnel may not implement proper safety related procedures. 11/23/10--Existing Related CAP: 2007-27. TIES/ENSS is in the process of revising and reformatting the ATC PMIs. The draft for all the PMIs is in the form of WMATA-1000. The revised procedures will have PMI number, description, date and revision number | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Improbable | 2012-03-31 | 2012-04-04 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000196 | Rail | Rules, Regulations, Procedures | Preventive Maintenance Documentation | 2012-04-19 | While ATC is working to implement MAXIMO, at the time of the review, ATC still used 30-year-old processes for PMI documentation. As a result, personnel may not implement proper safety related procedures. 11/23/10--Existing Related CAP: 2007-27. ATC will develop a written procedure/policy to include PMI “Measuring Points” within the Maximo System. The Measuring Points will be based on the Revised PMI Procedures. For PMI’s where “Measuring Points” are not | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000197 | Rail | Rules, Regulations, Procedures | Preventive Maintenance Documentation | 2012-04-17 | WMATA is in the process of revising ATC PMIs, some of which have not been changed since the early 1980s. As a result, personnel may not implement proper safety related procedures. 11/23/10--TIES/ENSS is in the process of revising and reformatting the ATC PMIs. The draft for all the PMIs is in the form of WMATA-1000. Draft copy was provided on November 5, 2010 for SMNT ATC management review to be completed by December 17, 2010. SM | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Improbable | 2012-03-31 | 2012-04-04 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000198 | Rail | Rules, Regulations, Procedures | Preventive Maintenance Documentation | 2012-04-17 | Some PMIs include multiple sets of instructions that may be confusing or allow for incorrect performance references when testing devices made by different manufacturers. As a result, personnel may not implement proper safety related procedures. 11/23/10--TIES/ENSS is in the process of revising and reformatting the ATC PMIs. The draft for all the PMIs is in the form of WMATA-1000. WMATA-1000 data sheets will be equipment manufacturer specific. The written instructions (PMIs) are segregated by e | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Improbable | 2012-03-31 | 2012-04-04 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000199 | Rail | Rules, Regulations, Procedures | Preventive Maintenance Documentation | 2012-04-19 | While WMATA is working to implement PMIs in the MAXIMO system, connection between incident work orders, maintenance work orders, and PMIs is not always clear. This could result in inadequate communication of safety related issues. 11/23/10--ATC will develop a Procedure/Policy that defines Incident Work Orders, Corrective Maintenance Work Orders, and Preventive Maintenance Work Orders in the Maximo System. This Procedure/Policy will delineate that each Incident Work Order must have | Inadequate communication of safety related issues. | Occasional | Negligible | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000200 | Rail | Rules, Regulations, Procedures | Preventive Maintenance Documentation | 2012-04-17 | It appears that SAFE is not included in the process for preparing and creating PMIs. Also, it appears that many PMIs are generated by Engineering Services without sufficient ATC input. This could cause a safety issue or concern related to ATC not adequately identified and communicated. 11/23/10--TIES/ENSS is in the process of revising and reformatting the ATC PMIs. The draft for all the PMIs is in the form of WMATA-1000. Draft copy was provided on November 5, 2010 for SMNT ATC management review to be completed by December 17, 2010. SM | Safety issue or concern related to ATC not adequately identified and communicated. | Remote | Critical | Improbable | 2012-03-31 | 2012-04-04 | Completed | McCoy, Darren | Negligible | 2D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000201 | Rail | Rules, Regulations, Procedures | Training and Certification Program | 2012-07-02 | While WMATA appears to be formalizing training records within a new data system, many records for (particularly) long-time employees are unavailable for review. This could result in inadequate training on safety related procedures and practices. 11/23/11--CENV/TTDC will develop a written plan to ensure all employee training records are available for review as an interim solution until PeopleSoft 7 training module is implemented. (January 2011). HR will also be implementing PeopleSoft 9.1 and the | Inadequate training on safety related procedures and practices. | Probable | Negligible | Remote | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4B - Acceptable with ESC review | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000202 | Rail | Rules, Regulations, Procedures | Preventive Maintenance Documentation | 2012-02-13 | WMATA has not fully documented joint track inspections for ATC and Track Maintenance. This could cause a safety issue or concern related to joint track inspections for ATC not being adequately communicated. 11/23/10--TRST will submit documentation from consultant (ZETA-TECH) referencing track inspection industry best practices regarding this issue. TRST will also submit General Superintendent memo dated August 1, 2010 stating joint track inspections are no | Safety issue or concern related to joint track inspections for ATC not adequately communicated. | Remote | Marginal | Improbable | 2011-06-30 | 2011-06-01 | Completed | McCoy, Darren | Negligible | 3D - Acceptable with ESC review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000203 | Rail | Management | Quality Assurance Funding | 2012-07-02 | While WMATA appears to have a plan and basis for a QA/QC Program, it appears to remain unfunded. This could cause inadequate QA/QC. | Inadequate QA/QC. | Remote | Negligible | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000204 | Rail | Rules, Regulations, Procedures | Maintenance Procedures for Power, Pump Equipment and Station Lighting | 2012-04-19 | Some Power maintenance topics, such as pump equipment and station lighting, are treated differently by different Power maintenance regions. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SMNT Power and ENSS is currently reviewing and updating Power preventive maintenance procedures. SMNT Power will also update the Maintenance management procedure to include a written plan for ensuring that all maintenance topics are implemen | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Marginal | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000205 | Rail | Rules, Regulations, Procedures | Housekeeping Maintenance Procedures | 2012-02-13 | Housekeeping issues (i.e., leaves, a cigarette butt) found in certain substation and tie-breaker locations were not identified properly by personnel demonstrating the Facility Inspection procedure. This could cause WMATA employee exposure to minor facility hazards due to inadequate housekeeping. 11/23/10--SMNT Power is currently evaluating our substation room inspection procedure to ensure that our house keeping issues are properly identified and addressed by the appropriate corrective actions. | WMATA employee exposure to minor facility hazards due to inadequate housekeeping. | Remote | Marginal | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 3D - Acceptable with ESC review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000206 | Rail | Rules, Regulations, Procedures | Housekeeping Maintenance Procedures | 2012-02-13 | Certain housekeeping issues (cobwebs, spiders, water intrusion) observed by the review team were reported several times by WMATA maintenance personnel, but were not addressed by any apparent corrective action. This could cause WMATA employee exposure to facility hazards due to inadequate corrective action of housekeeping issues. 11/23/10--SMNT Power is currently evaluating our substation room inspection procedure to ensure that our house keeping issues are properly identified and addressed by the appropriate corrective actions. | WMATA employee exposure to facility hazards due to inadequate corrective action of housekeeping issues. | Remote | Marginal | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 3D - Acceptable with ESC review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000207 | Rail | Rules, Regulations, Procedures | Traction Power Matenance Procedures | 2012-04-19 | Traction power maintenance and test sheets reviewed during this assessment were often incomplete, with steps such as battery terminal torqueing, DC breaker control wiring resistance, DC breaker contact resistance, and relay as-found measurements skipped, and in some instances with supervisor approval signatures missing. This could cause a loss of traction power in specific locations. 11/23/10--SMNT Power will update our Maintenance management procedure to include a formal process to ensure that all preventive maintenance inspections are completed in accordance with WMATA specifications and with the appropriate sign-off by superviso | Loss of Traction Power in specific locations. | Occasional | Negligible | Remote | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000208 | Rail | Facilities | Electrical Prints | 2012-02-13 | Substation K05 did not have station electrical prints on site. This could result in an inability to respond quickly and approrpriately during an emergency. 11/23/10--SMNT Power currently is evaluating our substation room inspection procedure to ensure that the requirement for electrical drawings in our substations are properly identified. Electrical prints are currently installed in Substation K05. | Inability to respond quickly and appropriately during an emergency. | Remote | Critical | Remote | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 2D - Undesirable - Management (ESC) decision | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000209 | Rail | Rules, Regulations, Procedures | Preventive Maintenance Documentation | 2012-07-02 | WMATA appears to lack clear, written measurement tolerances for traction power testing PMIs, such as for meggering, hi-pot testing, and resistance. This could result in poor traction of a train consist. 11/23/10--SMNT Power and ENSS is currently reviewing and updating Power preventive maintenance procedures. All measurements and tolerances will be added to the Preventive maintenance procedures. | Poor traction of train consist. | Remote | Catastrophic | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000210 | Rail | Rules, Regulations, Procedures | Power Inspection and Maintenance Procedures | 2012-04-19 | Power does not have a suitable departmental maintenance plan or similar document to guide inspection and maintenance practices throughout the WMATA Metrorail system. This could result in inadequate maintenance of the power system. 11/23/10--SMNT Power will review and update our maintenance management procedure to clearly specify inspection and maintenance practices for the entire Metrorail system. | Inadequate maintenance of power system. | Remote | Marginal | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000211 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 15, Maintenance Audits and Inspections | 2012-02-13 | The description and list of TSSM (Track Structure Systems Maintenance) inspections in Section 15.1 of the SSPP does not agree with the requirements in the Track Maintenance & Inspection Manual. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SSPP has been updated to reflect TOC, FTA and WMATA SAFE findings and recommendations. Draft of revised SSPP completed September 30, 2010, and is currently being reviewed internally by WMATA. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Remote | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000212 | Rail | Rules, Regulations, Procedures | Track Maintenance and Inspection Manual | 2012-02-13 | The Track Maintenance & Inspection Manual does not indicate the required inspection frequency for yard tracks. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--TRST will revise the Track Maintenance & Inspection Manual and Track Maintenance and Inspection Guidelines to indicate the required frequency for yard track inspection, to specify tolerances for switch inspection frequency, and to correct any di | Safety issue or concern related to yard tracks is not properly identified, reported, assessed, or mitigated. | Probable | Marginal | Remote | 2012-06-30 | 2011-06-14 | Completed | McCoy, Darren | Negligible | 3B - Undesirable - Management (ESC) decision | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000213 | Rail | Rules, Regulations, Procedures | Track Maintenance and Inspection Manual | 2012-02-13 | The Track Maintenance & Inspection Manual does not specify any tolerances for switch inspection intervals. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--TRST will revise the Track Maintenance & Inspection Manual and Track Maintenance and Inspection Guidelines to indicate the required frequency for yard track inspection, to specify tolerances for switch inspection frequency, and to correct any di | Safety issue or concern related to switches is not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2012-06-30 | 2011-06-14 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000214 | Rail | Rules, Regulations, Procedures | Emergency Rail Clamp Procedure | 2012-02-13 | There is no written procedure specifying the proper use and application of Emergency Rail Clamps. This could result in electrocution or shock. 11/23/10--TRST will develop a Work Instruction on the proper use and application of emergency rail clamps. TRST will provide the Work Instruction to TOC upon completion. | Electrocution or shock. | Occasional | Catastrophic | Improbable | 2012-06-30 | 2011-06-14 | Completed | McCoy, Darren | Negligible | 1C - Unacceptable | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000215 | Rail | Rules, Regulations, Procedures | Defect Monitoring | 2012-02-13 | WMATA appears to lack a consistent process to verify the status of any reported defects indicated as priority one (red). This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--TRST will develop a procedure for priority notification in Maximo for priority 1 defects and will submit this procedure to TOC upon completion. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Catastrophic | Improbable | 2012-06-30 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000216 | Rail | Rules, Regulations, Procedures | Track Inspector Training and Certification Programs | 2012-07-02 | Verification of inspector training and certification completion by required due dates is currently a manual process involving review of individual personnel training files. This could resut in inadequate training and certification of inspectors. 11/23/10--WMATA continues to implement the automated Access database process for tracking training data. HR will also be implementing PeopleSoft 9.1 and the 9.0 version of the Enterprise Learning Module beginning January 2011. Implementation of eLM is un | Inadequate training and certification of inspectors. | Remote | Negligible | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000217 | Rail | Rules, Regulations, Procedures | Defect Monitoring | 2012-02-13 | Track conditions and defect reports indicate the need for a continuing high level of inspection and maintenance on the Red Line north from Dupont Circle. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--TRST will provide TOC with an updated Work Plan/Business Plan that pertains to high priority inspection, maintenance and renewal process for the upper Red Line. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Probable | Catastrophic | Remote | 2012-06-30 | 2011-06-14 | Completed | McCoy, Darren | Negligible | 1B - Unacceptable | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000218 | Rail | Rules, Regulations, Procedures | Track Maintenance and Inspection Manual and Track Maintenance and Inspection Guidelines | 2012-02-13 | The Track Maintenance & Inspection Manual and the Track Maintenance & Inspection Guidelines differ for some content, figures, tables, and references. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--TRST will revise the Track Maintenance & Inspection Manual and Track Maintenance and Inspection Guidelines to indicate the required frequency for yard track inspection, to specify tolerances for switch inspection frequency, and to correct any di | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Remote | 2012-06-30 | 2011-07-22 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000219 | Rail | Rules, Regulations, Procedures | TSSM Safety Briefings | 2012-02-13 | WMATA lacks a formal process to ensure that TSSM safety briefings are always accurate and complete. This could result in a safety issue or concern not being properly communicated. 11/23/10--TRST will train all Roadway Workers in Charge and all Supervisors through the new RWP program which emphasizes a formal safety briefing process. TRST will submit the new safety briefing form and the RWP training program rosters upon completion | Safety issue or concern not properly communicated. | Probable | Negligible | Remote | 2011-04-30 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 4B - Acceptable with ESC review | 4D - Acceptable without review | 2010 Triennial Report
OHA_0000220 | Rail | Rules, Regulations, Procedures | ROW Safety Procedures | 2012-02-13 | WMATA is in the process of developing an entirely new ROW safety program and associated training; however, the current employee ROW safety training program has acute problems, including the omission of critical rules and procedures. This could result in a lack of adequate ROW training. 11/23/10--WMATA to evaluate the resources available to conduct required training programs to ensure that all training requirements will be completed. Provide the completed evaluation to TOC. WMATA to complete implementation of the new ROW safety program a | Lack of adequate ROW training. | Frequent | Catastrophic | Improbable | 2011-04-30 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 1A - Unacceptable | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000221 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Elemetn 13, Rules and Procedures Compliance | 2012-02-13 | Section 13.4 of the WMATA SSPP states that WMATA employees shall receive refresher ROW safety training every three years, but there has been no such refresher training program. This could result in a lack of adequate ROW training. 11/23/10--SAFE to revise SSPP to address new ROW program. Final revisions of SSPP to be provided to TOC by January 1, 2011. | Lack of adequate ROW training. | Frequent | Catastrophic | Improbable | 2011-01-01 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 1A - Unacceptable | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000222 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Elemetn 16, Training and Certification Review | 2012-07-02 | Section 16.2 of the WMATA SSPP states that SAFE works with certified training instructors from RAIL in formulating annual examinations on the MSRPH, but SAFE has not worked with Rail Training and Instruction in this capacity. This could result in inadequate technical expertise to accurately assess training needs. 11/23/10--SSPP updated to reflect TOC, FTA and WMATA SAFE findings and recommendations. Draft of revised SSPP completed September 30, 2010, and currently being reviewed internally by WMATA. Final revised SSPP to be provided to TOC by January 1, 2011. | Inadequate technical expertise to accurately assess training needs. | Remote | Negligible | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000223 | Rail | Rules, Regulations, Procedures | Mechanic Training Programs | 2012-04-18 | According to a review of records, at least 18 percent of Railcar Electromechanics and at least 41 percent of Mechanics have not completed training in their primary car blocks. This could result in railcar mechanics not being sufficiently qaulified to perform safety critical maintenance. 11/23/10--AGM TIES to develop a plan to ensure appropriate personnel complete training on electro mechanic and mechanic primary and secondary car blocks and other training, including backshop training. | Railcar mechanics insufficiently qualified to perform safety critical maintenance. | Remote | Critical | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Marginal | 2D - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000224 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Elemetn 16, Training and Certification Review | 2012-02-13 | Section 16.2 of the WMATA SSPP describes the current, outgoing training program for ROW safety. As a result, personnel may not implement proper safety procedures. 11/23/10--SAFE to revise the SSPP to address this finding. Final revised SSPP to be provided to TOC for review by January 1, 2011. | Personnel not implementing proper safety procedures. | Remote | Marginal | Improbable | 2011-01-01 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 3D - Acceptable with ESC review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000225 | Rail | Management | Rail Training and Instruction Staffing | 2012-02-13 | Rail Training and Instruction may not have sufficient resources to ensure that, moving forward, all train operators complete the required recertification requirements. Future resource restrictions could cause inadequate training of rail personnel. 11/23/10--Rail Training is lacking the appropriate levels of resources to ensure all required recertification requirements are met. Rail Training needs an increase in training instructors; training administrators; acquisition of equipment (copiers, scann | Future resource restrictions caus inadequate training of rail personnel. | Occasional | Negligible | Improbable | 2011-09-01 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000226 | Rail | Rules, Regulations, Procedures | RTRA Supervisor Training Program | 2012-02-13 | At the time of the review, the course outline for the RTRA Supervisor Training Program was in draft form. This could result in inadequate training of rail personnel. 11/23/10--RTRA to finalize and implement the RTRA Supervisor training program. | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2011-09-01 |  | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000227 | Rail | Rules, Regulations, Procedures | Training Program and Instruction Course Design, Development, Review and Revision | 2012-08-06 | WMATA does not have a process to ensure that training and instruction course design, development, review, and revision is completed consistently across all disciplines within the organization. This could result in inadequate training of rail personnel. 11/23/10--WMATA to develop a standardized system-wide course design process to be utilized by all divisions and departments that administer training programs. HR, in collaboration with all Metro training groups will establish and implement corporate Cour | Inadequate training of rail personnel. | Remote | Marginal | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000228 | Rail | Rules, Regulations, Procedures | Rail Operator Training Program | 2012-02-13 | WMATA lacks formal minimum criteria that must be met by bus operators in order to qualify to begin the Rail Operator Training Program. This could result in an unqualified operator. 11/23/10--Closed per TOC instruction. | Unqualified Operator. | Remote | Critical | Improbable | 2010-12-17 | 2010-12-01 | Completed | McCoy, Darren | Negligible | 2D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000229 | Rail | Rules, Regulations, Procedures | Employee Training and Certification Requirements | 2012-07-02 | WMATA lacks a formal plan, policy, or procedure to help ensure compliance with employee training and certification requirements. This could result in inadequate training of rail personnel. 11/23/10--WMATA to develop a plan that directs the monitoring of compliance with employee training and certification requirements. The completed plan will be provided to TOC. HR , in collaboration with TIES shall define and evaluate the existing business, | Inadequate training of rail personnel. | Remote | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000230 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-01-31 | WMATA does not yet have a compliant CM program or a plan for its achievement. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--CENV response: The foundation of CM for railcars is based on OPA 200-6, Engineering Modification Instruction. CENV will work with CENI to develop a configuration management implementation plan with an overall timeframe and intermediate mileston | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2013-01-13 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000231 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-01-31 | CM initiatives of other WMATA departments need to be addressed as part of an overall WMATA CM Plan. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--CENV response: The foundation of CM for railcars is based on OPA 200-6, Engineering Modification Instruction. CENV will work with CENI to develop a configuration management implementation plan with an overall timeframe and intermediate mileston | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2013-01-31 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000232 | Rail | Rules, Regulations, Procedures | Construction Safety and Environmental | 2012-05-22 | The WMATA Construction Safety and Environmental Manual does not address security. As a result, the current security system may not be sufficient. 11/23/10--SAFE to review the WMATA Construction Safety and Environmental Manual to determine the extent (if any) to which security issues should be addressed in this manual. | Current security system may not be sufficient. | Remote | Marginal | Improbable | 2012-05-31 | 2012-05-31 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000233 | Rail | Rules, Regulations, Procedures | Fitness For Duty Program | 2012-04-18 | Rail clerks are responsible for ensuring that train operators first reporting for their shifts are fit for duty, but do not receive training in reasonable suspicion. As a result, a train operator could work with diminished capacity. 11/23/10--RTRA to evaluate the feasibility of providing reasonable suspicion training to all rail clerks. | Train operator working with diminished capacity. | Remote | Catastrophic | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000234 | Rail | Rules, Regulations, Procedures | Drug and Alcohol | 2012-07-02 | The WMATA Drug and Alcohol Testing Policy, Version 7.21/5, remains in draft form. As a result, WMATA personnel supporting critical functions could be working at diminished capacity. 11/23/10--The revised Drug and Alcohol Policy has been revised, approved by FTA (provisions related to random drug testing report times) and is now under review by Labor. | WMATA personnel supporting safety critical functions are working with diminished capacity. | Remote | Catastrophic | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | 2010 Triennial Report
OHA_0000235 | Rail | Rules, Regulations, Procedures | System Safety Program Plan, Element 21, Procurement | 2012-02-13 | The Procurement SSPP section does not accurately describe current processes and does not comply with FTA and TOC requirements. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 11/23/10--SSPP updated to reflect TOC, FTA and WMATA SAFE findings and recommendations. Final revised SSPP to be provided to TOC by January 1, 2011. | Safety issue or concern related to procurement not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Improbable | 2011-01-01 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | 2010 Triennial Report
OHA_0000236 | Rail | Rules, Regulations, Procedures | Roadway Worker Protection Training Program | 2012-02-13 | Complete the Roadway Worker Protection (RWP) Training Program and ensure that employees, supervisors, and managers receive this training. Failure to do so could result in a lack of adequate Roadway Worker Protection training. 12/10/10--RWP Manual has been completed, signed off by GM,DGM, and CSO on August 24, 2010. New Employee training curriculum has been finalized. Gap Training (Level 4) curriculum for escort certified employees being finalized. Training-the-trainer commence | Lack of adequate Roadway Worker Protection (RWP) training. | Frequent | Catastrophic | Improbable | 2011-04-01 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 1A - Unacceptable | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000237 | Rail | Rules, Regulations, Procedures | Roadway Worker Protection Manual | 2012-02-13 | Establish a process to ensure that the Roadway Worker Protection Manual (RWP Manual), as well as the Washington Metropolitan Area Transit Authority’s (WMATA) safety policy and procedures, are followed. As a result, personnel may not implement proper safety procedures. 12/10/10--To ensure RWP manual is followed, TRST and SMNT supervisors and QAAW officers will conduct field audits; periodic briefings will also be held with staff; and monthly division safety committee meetings will be used to convey the safety message. I | Personnel do not implement proper safety procedures. | Probable | Marginal | Improbable | 2011-06-30 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 3B - Undesirable - Management (ESC) decision | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000238 | Rail | Rules, Regulations, Procedures | Safety Rules and Regulations | 2012-02-13 | Ensure that managers/supervisors are knowledgeable of and adhere to established safety rules and regulations, as well as provide proper oversight of Track and Structures Systems Maintenance (TSSM) employees. As a result, personnel may not implement proper safety related procedures. As of 10/12/10, TRST and SMNT have started supervisory audits of work areas to ensure all safety rules are being followed. Supervisors and managers are required to pass an annual test on rules and regulations as defined in the Metrorail Safety Rules and | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Improbable | 2011-04-30 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000239 | Rail | Rules, Regulations, Procedures | Roadway Worker Protection Rules | 2012-02-13 | Ensure that all employees have sufficient lighting when working along the ROW, rail, stations, mezzanines, outside parking lots, and revenue holding areas. As a result, personnel may not properly perform safety related duties. Maintenance crews are provided lighting for all work areas. Work sites are checked periodically to ensure there is sufficient lighting. If supplemental lighting is required, portable lighting is provided. Employees have been outfitted with various types o | Personnel do not properly perform safety related duties. | Remote | Negligible | Improbable | 2011-06-30 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000240 | Rail | Rules, Regulations, Procedures | SOP for Train Operator Personal Breaks | 2012-02-13 | Review the schedules of train operators to ensure that there are adequate allowances for bathroom and other personal breaks at the end of a line. As a result, personnel may not implement proper safety procedures. 1. All train schedules were reviewed prior to the June 2010 pick. All schedules are produced with at least seven minutes lay-over time for operators between trips. Schedules are designed to have drop-back operators during rush hour. In other words, operat | Personnel do not implement proper safety procedures. | Remote | Negligible | Improbable | 2010-10-25 | 2011-02-15 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000241 | Rail | Rules, Regulations, Procedures | Calibration Procedures for Precision Measurement Equipment | 2012-06-28 | Ensure that WMATA-owned precision measurement equipment is properly and timely calibrated and maintained. As a result, personnel may not properly perform safety related duties. A new "Test Equipment Calibration Procedure" has been developed. However, in order for the new procedure to be effectively carried-out, a clean-up of the Maximo Calibration database is required. The updated policy and procedure will allow management great | Personnel do not properly perform safety related duties. | Remote | Critical | Improbable | 2012-06-30 | 2012-06-30 | Completed | McCoy, Darren | Critical | 2D - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | TSSM IG Report December 10, 2010
OHA_0000242 | Rail | Rules, Regulations, Procedures | Personal Protective Equipment Procedures | 2012-02-13 | Ensure adequate personal protective equipment (PPE) is on hand to support maintenance activities and provide management oversight to supervisors to ensure they provide PPE to employees and enforce its use at all times. As a result, personnel may not properly perform safety related duties. Personnel are supplied with proper PPE at all times. Safety vests, eye and hearing protection are made available to all employees. Continual reinforcement of PPE is accomplished during daily tool box safety meetings and through issuance of "newly-focused" | Personnel do not properly perform safety related duties. | Remote | Catastrophic | Improbable | 2011-02-28 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 1D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000243 | Rail | Rules, Regulations, Procedures | TSSM Radio Procedures | 2012-02-13 | Provide all intended users in TSSM with the appropriate radios and related training to ensure adequate communications. This could result in inadequate communication of safety related issues. The new comprehensive radio communications system (CRCS) portable radios distribution started January, 2010. Currently, all departments have been issued their allotment. The conversion from the old VHF radios to the new CRCS mobile radios started in July | Inadequate communication of safety related issues. | Occasional | Negligible | Remote | 2011-04-30 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000244 | Rail | Management | TSSM Staffing | 2012-02-13 | Perform an assessment of TSSM’s staffing needs to ensure that adequate resources are available to meet maintenance objectives, including properly completing work orders in MAXIMO. Inadequate staffing could cause a safety issue or concern to go undetected, assessed, or mitigated. TRST and SMNT conducted a resource assessment of their respective areas in October 2010. The detailed plans were presented to the DGM during preliminary FY 2012 budget planning discussions. Business plans have been developed to highlight existing deficien | Inadequate staffing causes safety issue or concern to go undetected, assessed or mitigated. | Remote | Critical | Improbable | 2010-12-06 | 2011-02-15 | Completed | McCoy, Darren | Negligible | 2D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000245 | Rail | Rules, Regulations, Procedures | Infrastructure Renewal Program Training Programs | 2012-02-13 | Ensure that the Infrastructural Renewal Program-managed contracts for new equipment include training, schematics, and manufacturers’ manuals; and TSSM, in conjunction with the Office of Chief Engineer Vehicles, Technical Training and Document Control Branch, properly train employees to operate and service equipment and systems, including providing employees necessary training materials to operate and service equipment and systems assigned to them. This could result in inadequate or outdated safety documentation. All contracts are in the process of being rewritten to reflect new requirements for technical specifications, operations, and maintenance training. CENI has established a standard procedure that all RFP's and contracts include training. This process is on | Inadequate or outdated safety documentation. | Remote | Marginal | Improbable | 2011-06-30 | 2011-07-19 | Completed | McCoy, Darren | Negligible | 3D - Acceptable with ESC review | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000246 | Rail | Rules, Regulations, Procedures | TSSM Training Programs | 2012-07-02 | Develop a formal training program for TSSM employees that would enable them to successfully and safely carry out their duties and responsibilities. The program should include journeyman, supervisory, and technical training on operating and maintaining equipment used to support rail operations. The program should also include periodic refresher training for existing employees. This could cause inadequate training of rail personnel. A formal training program currently exists for craft employees which includes progressive training and refresher training where applicable. Pertinent craft training courses already exist in the curriculum for supervisory job codes. To ensure supervisors a | Inadequate training of rail personnel. | Remote | Critical | Improbable | 2014-06-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2D - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | TSSM IG Report December 10, 2010
OHA_0000247 | Rail | Rules, Regulations, Procedures | Supervisor Training Programs | 2012-07-02 | Ensure that supervisors/managers have the necessary training, knowledge, skills and abilities to effectively perform the assigned duties of their positions. This could cause inadequate training of rail personnel. TRST supervisors were presented with new work instructions for all work performed that list job hazard and risk. Track Standards (revised Nov 2009) and FRA training have been provided to employees (April 2010). In the most recent revision of the Craft Cur | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2014-06-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | TSSM IG Report December 10, 2010
OHA_0000248 | Rail | Rules, Regulations, Procedures | TSSM Communication Protocols | 2012-02-13 | Ensure there is effective communication up and down the chain of command by establishing strategic goals, objectives, and milestones that include proactive activities, embracing and instilling the need for open communication throughout the TSSM organization. This could cause inadquate communication of safety related issues. All departments within TRST and SMNT have established goals and objectives emphasizing worker's safety which are included in their Annual Performance Plan. Managers meet with staff on a regular basis and routinely make visits to union staff at their work | Inadequate communication of safety related issues. | Remote | Negligible | Improbable | 2011-09-30 | 2011-07-19 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000249 | Rail | Rules, Regulations, Procedures | TSSM Preventive Maintenance Insection System and Equipment Documentation | 2012-07-02 | Assess TSSM’s preventive maintenance inspection (PMI) system and equipment documentation needs and takes appropriate action to ensure that all PMIs are up-to-date and develop and test new PMIs prior to circulating them to technicians and mechanics. As a result, personnel may not implement proper safety related procedures. PMIs are up-to-date and are readily available to employees. CENI will develop: (a) a single manual of all Periodic Tests (ATC) Standards by March 2011; (b) standard drawings for circuits and mechanical drawings by June 2011; (c) Book of Plans for in servi | Personnel do not implement proper safety related procedures. | Occasional | Negligible | Remote | 2013-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000250 | Rail | Rules, Regulations, Procedures | TSSM Safety Committee | 2012-02-13 | Ensure that the results of local safety committees in TSSM are communicated to all TSSM employees; that safety concerns, if warranted, are resolved; and that local safety committees are established within Operations Control Center (OCC) and Maintenance Operations Center (MOC) and other offices not having a safety committee. A potential safety issue could result from inadequate communication of safety related issues. TRST and SMNT managers have been directed to post the divisional safety minutes within five days after meeting. Managers are instructed to ratify all employee concerns within 30 days and report back to the divisional safety committee meeting. All unresolv | Potential safety issue results from inadequate communication of safety related issues. | Occasional | Marginal | Remote | 2011-03-31 | 2011-04-26 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4D - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000251 | Rail | Rules, Regulations, Procedures | TSSM Safety Briefings | 2012-02-13 | Ensure that daily safety briefings provided by TSSM supervisors focus on current issues related to tasks being performed by their work crews. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. Job risk and hazards are discussed during safety briefings/debriefings and signatures for all attendees are required. TRST and SMNT has revised the daily "Rule of the Day" to reflect safety rules associated with work. Supervisors also have been instructed | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Remote | 2011-03-31 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4D - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000252 | Rail | Rules, Regulations, Procedures | OCC Training Program | 2012-02-13 | Ensure that OCC is provided training opportunities that include challenges and safety-related issues TSSM encounters on the ROW to help cultivate a shared appreciation of work responsibilities. A potential safety issue could result from inadequate or incomplete documentation. 1. All ROCC and MOC personnel will complete ROW and MSRPH training by Feb 2011. 2. Beginning January 2011, OCC will partner with TRST and SMNT to develop a familiarization exchange program. The program will be developed to give an opportunity for TRST, SM | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Remote | 2011-02-28 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000253 | Rail | Rules, Regulations, Procedures | MOC Training Program | 2012-07-02 | Ensure that (1) a formal training program is developed for all MOC personnel to provide them with technical knowledge and understanding of WMATA’s equipment and maintenance needs; (2) wayside operations procedures are put in place to effectively communicate with technical maintenance personnel in the field; and (3) a procedures manual for MOC operations and responsibilities is developed to ensure consistency of MOC operations. A potential safety issue could result from inadequate training, communication, or documentation for MOC personnel. 1. The exchange program mentioned in recommendation 3.5, MSRPH and ROW training will address recommendations (1) and (2) 2. By November 1, 2010, OCC Director will establish a team of (internal) individuals to study the development of a MOC procedure manua | Potential safety issue results from inadequate training, communication, or documentation for MOC personnel. | Remote | Marginal | Improbable | 2013-06-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | TSSM IG Report December 10, 2010
OHA_0000254 | Rail | Rules, Regulations, Procedures | OCC and MOC Communication Protocols | 2012-02-13 | Ensure that OCC management establishes a process that will foster better communications with MOC so the right information is provided to the responsible parties in a timely manner. This could cause inadequate communication of safety related issues. OCC Dir will create a document that outlines internal communication processes to include: * ROCC personnel responsibilities for reviewing all available bulletins, procedures, and other related information; *OCC Dir responsibility for providing staff with | Inadequate communication of safety related issues. | Occasional | Marginal | Remote | 2010-12-31 | 2011-03-15 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4D - Acceptable without review | TSSM IG Report December 10, 2010
OHA_0000255 | Rail | Rules, Regulations, Procedures | SOP for RTRA Development of Internal SOPs | 2012-08-06 | There is no RTRA SOP for development of internal SOPs. This could cause inadequate or outdated safety documentation. 12/29/10--Develop internal SOP on SOPs. | Inadequate or outdated safety documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000256 | Rail | Rules, Regulations, Procedures | RTRA Read Back/Hear Back Procedure | 2012-02-13 | No read back/hear back procedure. This could cause inadequate communication of safety related issues. 12/29/10--Develop a read back/hear back procedure for critical radio transmissions; this should include the conditions under which critical information passed by radio to the field is verified. | Inadequate communication of safety related issues. | Occasional | Marginal | Improbable | 2010-12-31 | 2011-06-22 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000257 | Rail | Rules, Regulations, Procedures | Pre-departure Train Inspection Verification Procedure | 2012-02-13 | No verification procedure in place for pre-departure train inspections. An inadequate inspection procedure could cause a safety issue or concern to go undetected, assessed or mitigated. 12/29/10--Develop and implement a checklist for the pre-departure inspection and a verification procedure, including sign-offs and QC | Inadequate inspection procedure causes safety issue or concern to go undetected, assessed or mitigated. | Occasional | Marginal | Remote | 2011-05-31 | 2011-07-19 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4D - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000258 | Rail | Rules, Regulations, Procedures | RTRA Security Training Program | 2012-04-19 | Lack of training for security. A security issue or concern may not be properly identified, reported, assessed, or mitigated. 12/29/10--Ensure that security and related training for areas of concern is provided to RTRA employees: Refer to item 32 j in the audit matrix. | Security issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000259 | Rail | Rules, Regulations, Procedures | RTRA Continuity of Operation Plan | 2012-04-19 | Lack of procedures to support Continuity of Operation Plans (COOP). A potential safety issue results from inadequate or incomplete procedures during mild or severe system diruptions. 12/29/10--Develop departmental procedures to support activation of the WMATA COOP | Potential safety issue results from inadequate or incomplete procedures during mild or severe system disruption. | Remote | Critical | Improbable | 2013-03-31 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2D - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000260 | Rail | Rules, Regulations, Procedures | RTRA Facility Emergency Plans or Procedures | 2012-07-02 | No specific facility emergency plans or procedures. This could cause an inability to respond effectively in a fire/life safety emergency. 12/29/10--Develop facility emergency plans and procedures for each division, to include all-hazards scenarios, including active shooter, weather emergencies, fire, shelter-in-place options, etc. Develop OCC COOP and supporting SOPs; as appropriate, develo | Inability to respond effectively in a fire/life safety emergency. | Remote | Catastrophic | Improbable | 2013-03-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000261 | Rail | Rules, Regulations, Procedures | RTRA Continuity of Operation Plan | 2012-04-19 | Lack of exercises to test COOPs. As a result, personnel may not properly perform safety related duties. 12/29/10--Hold annual exercises to test RTRA COOPs; ensure that SOPs are developed within RTRA to facilitate participation in drills, critical debriefings and corrective actions from items identified in emergency preparedness drills. | Personnel do not properly perform safety related duties. | Remote | Catastrophic | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000262 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-02-13 | Critical documentation is not readily available to control center employees. This could cause an inability to respond effectively in a critical situation. 12/29/10--Ensure that all critical documentation is updated properly and readily available to everyone on duty as appropriate in the control center. | Inability to respond effectively in a critical situation. | Probable | Catastrophic | Improbable | 2010-12-31 | 2011-06-22 | Completed | McCoy, Darren | Negligible | 1B - Unacceptable | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000263 | Rail | Rules, Regulations, Procedures | RTRA SOP for Issuance/Receipt of all Shift Information for Controllers | 2012-02-13 | There is no SOP or verification process for issuance/receipt of all shift information for controllers. This could result in inadequate communication of safety related issues. 12/29/10--Develop a formal SOP and supporting checklists/documentation for the controller shift changes to ensure accountability and correct exchange of critical safety information between shifts. | Inadequate communication of safety related issues. | Occasional | Catastrophic | Remote | 2011-08-31 |  | Completed | McCoy, Darren | Catastrophic | 1C - Unacceptable | 1D - Undesirable - Management (ESC) decision | RTRA ISA Report December 29, 2010
OHA_0000264 | Rail | Rules, Regulations, Procedures | RTRA SOP for General Order and Track Right Authorization System (GOTRS) | 2012-02-13 | There is no SOP for controllers to ensure that the information contained in the General Order and Track Right Authorization System (GOTRS) is properly reviewed prior to each shift . This could result in inadequate communication of safety related issues. 12/29/10--Develop a formal SOP and accountability for controller review of the GOTRS information on each shift. | Inadequate communication of safety related issues. | Probable | Catastrophic | Improbable | 2011-08-31 |  | Completed | McCoy, Darren | Catastrophic | 1B - Unacceptable | 1E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000265 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-02-13 | SAFE does not currently review any Rail Transportation (RTRA) documentation. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 12/29/10--Ensure that all RTRA documentation is reviewed by Safety for compliance with the SSPP and safety requirements | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Marginal | Improbable | 2011-09-30 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 3D - Acceptable with ESC review | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000266 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-04-19 | No SOPs or procedures in place for Configuration Management & Document Control. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 12/29/10--Ensure that there are formal, documented procedures for configuration management and document control for all areas of RTRA; Documentum system is being implemented, but SOPs for its use must be developed for each area. This includes all logs, in | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000267 | Rail | Rules, Regulations, Procedures | Emergency Responder Training Programs | 2012-07-02 | Area emergency response partners have not been trained in the unique configuration of the JGB and CTF control centers. This could cause an inability to respond effectively in a fire/life safety emergency. 12/29/10--Include control center facilities in emergency responder training | Inability to respond effectively in a fire/life safety emergency. | Remote | Catastrophic | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000268 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-02-13 | Some RTRA documentation, especially logs, is not collected or stored electronically. Many of these items also do not have SOPs for their use, and do not have QC performed. An indirect hazard could result due to inadequate or incomplete reporting of unacceptable hazardous conditions. 12/29/10--All required documentation, including logs, requires SOPs to guide the completion of the task. Electronic means of completing the task may improve processes. In addition, having Maximo available to Station Managers would be of great benefit an | Indirect hazard may occur due to inadequate or incomplete reporting of unacceptable hazardous conditions. | Remote | Negligible | Improbable | 2011-03-31 |  | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000269 | Rail | Rules, Regulations, Procedures | RTRA SOP for Radio Troubleshooting | 2012-02-13 | No SOP in place for radio troubleshooting. This could cause inadequate communication of safety related issues. 12/29/10--Need SOP for radio troubleshooting | Inadequate communication of safety related issues. | Occasional | Negligible | Improbable | 2011-08-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000270 | Rail | Rules, Regulations, Procedures | RTRA SOP for Superintendent and Assistant Superintendent Work Responsibilities | 2012-04-19 | Superintendents and Assistant Superintendents do not have SOPs or methodologies to cover their work. As a result, personnel may not implement proper safety procedures. 12/29/10--Develop SOPs or methodologies for all work tasks for Superintendents and Assistant Superintendents | Personnel not implementing proper safety procedures. | Remote | Marginal | Improbable | 2013-03-31 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000271 | Rail | Rules, Regulations, Procedures | Safety Criticality of Control Center Activities | 2012-02-13 | Safety criticality of control center activities is not formally established. As a result, personnel may not implement proper safety related procedures. 12/29/10--Ensure that documentation of all safety-critical processes in the control center is in place. | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2011-09-30 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000272 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-02-13 | SAFE does not currently review any RTRA training programs. Programs are also not reviewed by other stakeholders. This could result in inadequate training of rail personnel. 12/29/10--Ensure that all training programs are reviewed by safety for compliance with the SSPP and other safety ; by MTPD for security/SEPP compliance; and by other stakeholders as appropriate. | Inadequate training of rail personnel. | Occasional | Marginal | Remote | 2011-09-30 |  | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000273 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-05-22 | There is no SOP for regular review, revision and update of all internal RTRA documentation. A potential safety issue my result from inadequate or incomplete documentation. 12/29/10--Develop an SOP for the review, revision and update of all RTRA documentation, to include the review and approval process with safety review and signoff | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-05-31 | 2012-05-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000274 | Rail | Rules, Regulations, Procedures | Safety Certification Processes | 2012-04-19 | RTRA does not significantly participate in safety certification, end-user input or life-cycle planning. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 12/29/10--Ensure full participation of RTRA in all procurements from planning to disposal for all equipment and other purchases. Ensure that safety certification is performed for all safety-critical procurements, and that RTRA and Safety participate. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Remote | Marginal | Improbable | 2012-12-31 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000275 | Rail | Rules, Regulations, Procedures | RTRA SOP for Trend Analysis | 2012-08-06 | There are no SOPs for trend analysis and other reporting performed by RTRA. An indirect hazard may occur due to inadequate or incomplete reporting of unnaceptable hazardous conditions. 12/29/10--Ensure that responsibilities and SOPs/methodologies for all trend analysis and reporting are captured (see R16) | Indirect hazard may occur due to inadequate or incomplete reporting of unacceptable hazardous conditions. | Remote | Negligible | Improbable | 2012-12-31 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000276 | Rail | Rules, Regulations, Procedures | Accident Investigation Procedure | 2012-04-19 | Complete documentation for participation of RTRA personnel in accident and incident investigation is not in place. As a result, personnel may not implement proper safety relatd procedures. 12/29/10--Ensure that complete formal documentation for all investigations is in place for RTRA personnel. | Personnel do not implement proper safety related procedures. | Occasional | Marginal | Improbable | 2012-03-31 | 2012-03-31 | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000277 | Rail | Rules, Regulations, Procedures | RTRA Training Program | 2012-02-13 | No training policy or matrix for RTRA personnel. This may cause inadequate training of rail personnel. 12/29/10--Develop a formal training policy and matrix for all RTRA personnel, including Superintendents. | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2011-12-31 |  | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000278 | Rail | Rules, Regulations, Procedures | Fitness For Duty Program | 2012-02-13 | No verification of fitness for duty checks for operators is performed. Potentially unfit operators may be placed into service. 12/29/10--Implement standards, guidelines, SOPs and verification for fitness for duty checks. | Potential unfit operator. | Remote | Critical | Improbable | 2011-01-31 | 2011-09-20 | Completed | McCoy, Darren | Negligible | 2D - Undesirable - Management (ESC) decision | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000279 | Rail | Rules, Regulations, Procedures | OEM Desk Function SOP | 2012-02-13 | OEM desk function is not covered in RTRA SOPs. A potential safety issue may result from inadequate or incomplete documentation. 12/29/10--Ensure that SOPs for OEM desk functions are developed and implemented. | Potential safety issue result from inadequate or incomplete documentation. | Remote | Marginal | Improbable | 2011-05-31 | 2011-06-22 | Completed | McCoy, Darren | Negligible | 3D - Acceptable with ESC review | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000280 | Rail | Rules, Regulations, Procedures | RTRA SOP for Lost Key Prevention | 2012-02-13 | No SOPs in place for loss prevention regarding keys. This could degrade security. 12/29/10--Develop and implement SOPs for loss prevention for keys issued to RTRA personnel. | Lost key. | Remote | Catastrophic | Improbable | 2011-05-31 |  | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | RTRA ISA Report December 29, 2010
OHA_0000281 | Rail | Rules, Regulations, Procedures | RTRA Interdepartmental Coordination SOP | 2012-08-06 | Not all interdepartmental coordination is covered by formal SOPs. This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. 12/29/10--Develop SOPs for all interdepartmental coordination. | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Negligible | Remote | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000282 | Rail | Rules, Regulations, Procedures | RTRA SOP 35, Cranking and Blocking | 2012-02-13 | Cranking and blocking procedure (SOP 35) is not clearly defined and fully implemented agency-wide. This could result in improper cranking and blocking of switches. 12/29/10--Cranking and blocking procedure needs to be evaluated and revised to ensure responsibilities, equipment and procedures are fully documented. | Improper cranking and blocking of switches. | Occasional | Catastrophic | Remote | 2011-01-31 | 2011-06-28 | Completed | McCoy, Darren | Negligible | 1C - Unacceptable | 4D - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000283 | Rail | Rules, Regulations, Procedures | RTRA General Order and Track Right Authorization System Contingency Plan | 2012-02-13 | No contingency plan is in place for loss of the General Order and Track Right Authorization System (GOTRS) system. A potential safety issue may result from inadequate or incomplete procedures during mild of severe system disruption. 12/29/10--Develop and implement a contingency plan for full, partial, short- and long-term loss of the GOTRS system. | Potential safety issue results from inadequate or incomplete procedures during mild or severe system disruption. | Occasional | Critical | Remote | 2011-08-31 |  | Completed | McCoy, Darren | Critical | 2C - Undesirable - Management (ESC) decision | 2D - Undesirable - Management (ESC) decision | RTRA ISA Report December 29, 2010
OHA_0000284 | Rail | Rules, Regulations, Procedures | RTRA Superintendent and Assistant Superintendent Track Circuitry Error Reporting Training | 2012-02-13 | Superintendents and Assistant Superintendents do not have adequate training on track circuitry error reporting. Inadequate training of rail personnel results in safety issue or concern. 12/29/10--Ensure that all Personnel handling BCH errors are adequately trained in this critical area | Inadequate training of rail personnel. | Occasional | Marginal | Improbable | 2011-12-31 | 2011-06-22 | Completed | McCoy, Darren | Negligible | 3C - Undesirable - Management (ESC) decision | 4E - Acceptable without review | RTRA ISA Report December 29, 2010
OHA_0000285 | Rail | Rules, Regulations, Procedures | Escalator/Elevator Preventive Maintenance Practices | 2012-04-19 | Provide sufficient lighting for a safe working environment. Personnel do not properly perform sfaety related duties. WMATA has commissioned a Lighting & Re-Lamping Project which is spearheaded by WMATA IRPG. The initial Lighting & Re-Lamping efforts are planned to begin2/13/11 @ the Shady Grove Station, the first phase will cover the entire Red Line | Personnel do not properly perform safety related duties. | Remote | Negligible | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | VTX Elevator and Escalator Report
OHA_0000286 | Rail | Rules, Regulations, Procedures | Escalator/Elevator Operation and Maintenance | 2012-04-19 | Provide for removal of water in machine rooms and pit areas. Failure to do so could result in a WMATA employee being exposed to facility hazards due to water in machine rooms and pit areas. As part of the Lighting & Re-Lamping Project an initial field level water intrusion survey will be completed. The survey will be completed by an independent structural engineer assigned by IRPG. The survey results will provide information needed to develo | WMATA employee exposure to facility hazards due to water in machine rooms and pit areas. | Remote | Catastrophic | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | VTX Elevator and Escalator Report
OHA_0000287 | Rail | Rules, Regulations, Procedures | Escalator/Elevator Operation and Maintenance | 2012-04-18 | Modify escalator machine room entrances where possible to eliminate ships ladder access. (Dupont South example) This could result in a safety issue or concern not being properly identified, reported, assessed, or mitigated. The ELES Parts & Contracts group have made Bilco Ladder Ups a stock item. ELES has installed ladder ups at DuPont Circle, Stadium Armory, & Judiciary Square. ELES to survey the entire Elevator & Escalator system to identify all locations requiring the Lad | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Probable | Critical | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Critical | 2B - Unacceptable | 2E - Acceptable with ESC review | VTX Elevator and Escalator Report
OHA_0000288 | Rail | Rules, Regulations, Procedures | Escalator/Elevator Operation and Maintenance | 2012-02-13 | Provide appropriate storage cabinets and containers in machine rooms as necessary for safe storage of materials and tools. Failure to do so may result in personnel not implementing proper safety procedures. A new storage cabinet design has been identified and a PO has been issued to procure the new cabinets. The new cabinets are elevated to prevent water intrusion. Installation will be completed as they are received from the vendor warehouse | Personnel do not implement proper safety procedures. | Occasional | Marginal | Remote | 2011-09-30 |  | Completed | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | VTX Elevator and Escalator Report
OHA_0000289 | Rail | Rules, Regulations, Procedures | Escalator/Elevator Operation and Maintenance | 2012-04-18 | All escalator brakes have questionable stopping performance under no load with respect to their ability to stop and hold a full passenger load, i.e., no-load stopping distances appear to be too long for the inertia-mass brake systems utilized. Testing procedures need to be improved; the stopping distances must be recorded during the required testing schedule. Failure to do so could result in an escalator stopping too slowly wiht a full load of passengers in an emergency. | Escalator stops too slowly with a full load of passengers in an emergency | Probable | Critical | Occasional | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Critical | 2B - Unacceptable | 2C - Undesirable - Management (ESC) decision | VTX Elevator and Escalator Report
OHA_0000290 | Rail | Rules, Regulations, Procedures | Drug and Alcohol | 2012-08-06 | There is no formal Standard Operating Procedure (SOP) for dissemination of the WMATA Drug and Alcohol policy and procedures document. A potential safety issue results from inadequate or incomplete documentation. Develop a formal SOP for dissemination of the WMATA Drug and Alcohol policy and procedures document. It can be part of the policy and procedures document. See #4 below. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Drug and Alcohol Internal Audit
OHA_0000291 | Rail | Rules, Regulations, Procedures | Drug and Alcohol | 2012-08-06 | Current Policy has not bee revised since 2002. A potential safety issue results from inadequate or incomplete documentation. Current policy is under revision process at this time and is expected to be in place by October 1, 2010. A formal SOP needs to be added to the policy document to indicate annual review and version control. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Drug and Alcohol Internal Audit
OHA_0000292 | Rail | Rules, Regulations, Procedures | Drug and Alcohol | 2012-02-13 | Current EAP program has no formal SOP. A potential safety issue results from inadequate or incomplete documentation. Formal SOPs for the EAP Program should be documented for use throughout the Authority. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2011-08-18 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Drug and Alcohol Internal Audit
OHA_0000293 | Rail | Rules, Regulations, Procedures | Drug and Alcohol | 2012-07-02 | No data analysis reports for testing of WMATA employees are currently being performed on drug and alcohol testing. A potential safety issue results from inadequate or incomplete documentation. Drug and alcohol testing results with redacted personal/medical identifying information are to be forwarded to the Safety Department for review and analysis. The Safety Department shall make a formal request in writing to ensure the data is transmitted f | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Remote | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | 2010 Drug and Alcohol Internal Audit
OHA_0000294 | Rail | Rules, Regulations, Procedures | Drug and Alcohol | 2012-07-02 | Data is not currently shared with other departments for analysis and review. A potential safety issue results from inadequate or incomplete documentation. Drug and alcohol testing results with redacted personal/medical identifying information are to be forwarded to the Safety Department for review and hazard analysis, and transmittal to other departments for review as appropriate based on that analysis. An | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Marginal | Remote | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3C - Undesirable - Management (ESC) decision | 3D - Acceptable with ESC review | 2010 Drug and Alcohol Internal Audit
OHA_0000295 | Rail | Rules, Regulations, Procedures | Drug and Alcohol | 2012-08-06 | No system-wide SOPs exist for implementation of sanctions per 49 CFR 655. A potential safety issue results from inadequate or incomplete documentation. Develop WMATA SOPs for use throughout the agency for sanctions related to 49 CFR 655. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Drug and Alcohol Internal Audit
OHA_0000296 | Rail | Rules, Regulations, Procedures | Configuration Management Policy | 2012-08-06 | No change control (Configuration Management) SOPs exist for Medical Group documentation. A potential safety issue results from inadequate or incomplete documentation. Development of formal configuration management/ document control procedures are needed for the Medical Group. | Potential safety issue results from inadequate or incomplete documentation. | Occasional | Negligible | Remote | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4C - Acceptable without review | 4D - Acceptable without review | 2010 Drug and Alcohol Internal Audit
OHA_0000297 | Rail | Rules, Regulations, Procedures | Medical Group Training Programs | 2012-08-06 | There is no formal training program in place for Medical Group employees. This may result in inadequate training on safety related procedures and practices. A formal training program needs to be developed for the department, including a training matrix and policy. | Inadequate training on safety related procedures and practices. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Drug and Alcohol Internal Audit
OHA_0000298 | Rail | Rules, Regulations, Procedures | SOP for Self-Referral Program | 2012-02-13 | There are no SOPs in place for use system-wide for the self-referral program. A potential safety issue results from inadequate or incomplete documentation. Develop WMATA SOPs for use throughout the agency for the self-referral program. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2011-08-18 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | 2010 Drug and Alcohol Internal Audit
OHA_0000299 | Rail | Rules, Regulations, Procedures | Rail Contractor Drug Testing and Auditing Program | 2012-02-13 | Rail Contractor drug testing/auditing program is currently not being implemented. As a result, a safety issue or concern is not properly identified, reported, assessed, or mitigated. 1. Ensure the Medical Group has a list of the contractors currently working in rail. 2. Development of an SOP to ensure notification of the Medical Group any time a contractor begins work for TSSM. 3. Ensure the applicable contractor audits are performed | Safety issue or concern not properly identified, reported, assessed, or mitigated. | Occasional | Catastrophic | Remote | 2010-12-21 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 1C - Unacceptable | 4D - Acceptable without review | 2010 Drug and Alcohol Internal Audit
OHA_0000300 | Rail | Rules, Regulations, Procedures | Drug and Alcohol Policy | 2012-07-02 | No departmental information security SOPs were provided. A potential safety issue results from inadequate or incomplete documentation. Development of departmental SOPs for information security. These can be part of the Departmental policy and guidelines. | Potential safety issue results from inadequate or incomplete documentation. | Improbable | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3E - Acceptable with ESC review | 3E - Acceptable with ESC review | 2010 Drug and Alcohol Internal Audit
OHA_00301 | Rail | Track Environmentq | Running Rails | 2011-08-12 | Correct out of tolerance track conditions. | Track was out of tolerance leading to a derailment. CAP required repair of specific track condition, review and enhancment of maintenance procedures and quality conformance checks. | Occasional | Catastrophic | Improbable | 2011-06-28 | 2011-06-28 | Completed | Maniuszko, Robert P. | Negligible | 1C - Unacceptable | 4E - Acceptable without review | Rail Accident Report
OHA_00302 | Rail | Passenger Emergency Response System | Rollover | 2012-07-02 | Multiple Elevator Intercoms failed to rollover within the standard 45 second timeframe. Many rollover calls were not answered by ROCC. Multiple Kiosks were not equipped with the flashing yellow strobe and emergency tone. Multiple Elevator Intercoms were found not functioning due to equipment failure. | The hazard presented by the failure of the PERS is that an individual could remain trapped within an elevator for a long period of time without proper response from staff, FD or EMS. | Probable | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | Maniuszko, Robert P. | Negligible | 3B - Undesirable - Management (ESC) decision | 4E - Acceptable without review | ADA QA Specialist - Keisha White
OHA_00307 | Rail | Rules, Regulations, Procedures | Quality Assurance Program | 2012-06-28 | Quality Assurance Program should be established to monitor compliance with TSSM Procedures. | There are no established procedures to monitor compliance | Remote | Marginal | Improbable | 2012-06-30 | 2012-06-30 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | Derailment Report
OHA_00308 | Rail | Rules,Regulations, Procedures | Operations Administrative Procedure | 2012-04-20 | Revise OAP 208-01 | Procedure is outdated and not useful in its current state | Improbable | Marginal | Not Rated | 2011-06-30 | 2011-06-30 | Completed | McCoy, Darren | Negligible | 3E - Acceptable with ESC review |  | Derailment Report
OHA_00309 | Rail | Rules, Regulations, Procedures | Lockout/Tagout Procedure | 2012-04-20 | Installation of LOTO labels. | Electrocution or shock | Remote | Critical | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Critical | 2D - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | Arc Flash
OHA_00310 | Rail | Rules,Regulations,Procedures | Training | 2012-04-20 | Retrain all Department personnel | Inadequate training of personnel | Remote | Negligible | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Arc Flash
OHA_00311 | Rail | Rules,Regulations,Procedures | Training | 2012-04-20 | Retrain and recertify operator with emphasis on safety stops and monitoring the peoper operation of the train. | Employee does not follow procedures. | Remote | Negligible | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Bump Post Incident
OHA_00312 | Rail | Rules,Regulations,Procedures | Track Maintenance Procedure | 2012-04-20 | The derail units in all of the Authority's pcoket tracks, side tracks, storage tracks on mainline, yard, and secondary tracks be painted with high-visibility paint that aids in the identification of these devices. | Track obstruction. | Remote | Catastrophic | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Flat Car Derailment
OHA_00313 | Rail | Rules,Regulations,Procedures | Maintenance Procedure | 2012-04-20 | The Automatic Train Control (ATC) group be given the responsibility of ensuring that the derail units are maintained in their high-visibility state during monthly inspections performed by ATC. | Track obstruction. | Remote | Catastrophic | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Flat Car Derailment
OHA_00314 | Rail | Rules,Requlations,Procedures | Training | 2012-06-28 | The Rail Operations Control Center (ROCC) develop test questions that will be included on the annual training and certification program for OCC controllers that will include operational functions, locations, or other related and pertinent information regarding derail units currently deployed throughout the WMATA system. | Inadequate training of rail personnel. | Remote | Negligible | Improbable | 2012-06-30 | 2012-06-30 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Flat Car Derailment
OHA_00315 | Rail | Rules,Requlations,Procedures | Standard Operating Procedures | 2012-04-20 | Nomenclature be adopted between the OCC controller and the ATC technician to include instructions for blocking and cranking switches for all of the pocket track locations that will include instuctions for ATC technician to check and verify the status of the derail unit as part of the cranking and blocking procedures and/or instructions. | Potential safety issue results from inadequate or unclear communications. | Remote | Marginal | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | Flat Car Derailment
OHA_00316 | Rail | Rules,Regualtion,Procedures | Training | 2012-08-06 | The current TSSM operator and flagging classes adopt training measures that clearly provide training on the use, location, purpose, and scope of mechanical and remote-controlled derail unis currently installed tthroughout the Authority's railway system. | Inadequate training of rail personnel. | Remote | Negligible | Improbable | 2012-08-31 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Flat Car Derailment
OHA_00317 | Rail | Rules,Regulation , Procedures | Training | 2012-06-28 | The current TSSM training be amended to include a requirement for a complete ground walk-around inspection whenever unusual occurrences are observed or reported incvolving the work train consist. | Inadequate training of rail personnel. | Remote | Negligible | Improbable | 2012-06-30 | 2012-06-30 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Flat Car Derailment
OHA_00318 | Rail | Rules,Regulation,Procedures | Standard Operating Procedure | 2012-04-20 | A recommendation be made to the Metrorail Safety Rules and Procedures Handbook Committee to review and add additional language to the existing Standard Operating Procedure (SOP #35.3) or within the subpart of this SOP that will include instructions, protocol, and reference to the locations, operations, and responc=sibilities associated with all derail units currently installed throughout the Authority's railway system. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Marginal | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | Flat Car Derailment
OHA_00319 | Rail | Rules, Regulation,Procedure | Signage | 2012-04-20 | Signage similar to that currently deployed that indicate vent shafts, chain markers, and other pertinent information along the right-of-way be installed at each pocket track location where a derail unit is currently installed. This is to provide additional visible warning and knowlledge that the device is installed. | Track obstruction. | Remote | Catastrophic | Improbable | 2011-06-30 | 2011-06-30 | Completed | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Flat Car Derailment
OHA_00320 | Rail | Rules,Regulation,Procedures | Standard operating Procedures | 2012-04-20 | The MSRPH Glossary of Metrorail Terminology be updated to include the term derail unit. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2011-06-30 | 2011-06-30 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Flat Car Derailment
OHA_00321 | Rail | Rules,Regulation,Procedures | Training | 2012-04-20 | ATC Training certification for cranking and blocking procedures be amended to include instructions and/or procedures related to the operations, verification, and inspection of the Authority's derail units. | Inadequate training of rail personnel. | Remote | Negligible | Improbable | 2012-02-29 | 2012-02-29 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Flat Car Derailment
OHA_00322 | Rail | Railcar | vital relays | 2012-08-06 | All carborne Type B1 vital relays manufactured before 1996 shall be replaced or serviced and updated to the latest configuration (stainless steel residual screw) per Alstom's recommendation (Refer to Appendix O). The relays in the USR and FSBR locations will be updated first, as applicable on the various fleets. Service Bulletins have been released for the 1000, 2000, 3000, 5000, and 6000 vehicle fleets as shown in Appendix P. | Train overruns signal; does not stop as commanded. | Remote | Catastrophic | Improbable | 2012-10-31 |  | Implementing Corrective Actions | McCoy, Darren | Catastrophic | 1D - Undesirable - Management (ESC) decision | 1E - Acceptable with ESC review | Potomac Overrun
OHA_00323 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | Although laboratory tests did not identify the otrigin of the contamination of the subject vital relay, WMATA's internal inspection and testing processes should be revised to eliminate any potential sources of contamination from foreign substances. CENV should integrate the enhanced inspection and testing protocol developed by ATC-Engineering into the vehicle maintenance procedures. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-10-31 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Potomac Overrun
OHA_00324 | Rail | Railcar | Vital Relay | 2012-07-02 | CMNT should procure improved bench test equipment that will enable CMNT to track vital relay performance over time to identify relays with declining release performance. Commercially available test equipment has been identified and evaluated in support of this effort. | Potential safety issue results from inadequate or unavailable equipment. | Remote | Negligible | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Potomac Ave Overrun
OHA_00325 | Rail | Railcar | Vital Relay | 2012-08-06 | A technical survey was developed concerning the testing and maintenance practices for the Alstom B1 vital relays. The survey will be distributed to other transit agencies to d=identify the best practives for the service and testing of these relays. Refer to Appendix Q for the survey Questions. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-10-31 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Potomac Ave Overrun
OHA_00326 | Rail | Rules,Regulations,Procedures | Training | 2012-08-06 | CMNT technicians no longer operate rail cars into and out of the rail facilities and in the yard until a formal training process to qualify CMNT shop personnel is developed. | Potential safety issue results from inadequate or unavailable equipment. | Remote | Negligible | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | Hard Coupling 8/26/09
OHA_00327 | Rail | Information Technology | AIMS | 2012-07-02 | "SCADA systems are not properly identified as SCADA and are compartmentalized SCADA systems: 1. TIES SCADA a. ELES (This system must be maintained and monitored separately to conform tyo federal law) b. AIM, including Automatic Train Control, in train control rooms, ROCS: and power management and distribution c. Advanced energy d. ADT alarm and security camera system 2. PLNT SCADA system--control energy management (Lighting at stations and facilities) 3. PIDS (currently protected fully through MITS)." | Inability to accurately monitor rail operations and key systems. | Remote | Critical | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Critical | 2D - Undesirable - Management (ESC) decision | 2E - Acceptable with ESC review | IT ISA 3/27/11
OHA_00328 | Rail | Rules,Regulation,Procedures | Standard Operating Procedure | 2012-08-06 | IT documentation is not reviewed by Safety or MTPD. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-07-31 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | IT ISA 3/27/2011
OHA_00329 | Rail | Rules,Regulations,Procedures | Training | 2012-05-31 | IT does not currently perform internal control activities for all of its required functions. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2011-08-15 | 2011-08-15 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | IT ISA 3/27/11
OHA_00330 | Rail | Rules,Regulation,Procedures | Standard operating Procedure | 2012-08-06 | IT does not currently have a documented training policy, procedures, or matrix for its employees. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-10-07 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | IT ISA 3/27/11
OHA_00331 | Rail | Rules,Regulation,Procedures | Compliance | 2012-07-02 | IT does not currently comply with the WMATA Safety and Security Certification program. | Personnel do not implement proper safety procedures. | Remote | Marginal | Improbable | 2012-09-30 |  | Implementing Corrective Actions | McCoy, Darren | Marginal | 3D - Acceptable with ESC review | 3E - Acceptable with ESC review | IT ISA 3/27/11
OHA_00332 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | IT does not currently have documented a full maintainability program including life-cycle program planning and hazardous materials disposal. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2013-04-07 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | IT ISA 3/27/11
OHA_00333 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | The Disaster Recovery site has only checklists and spreadsheets to document its PM activities. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | IT ISA 3/27/11
OHA_00334 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | Day-to day operations of the department are not formally documented in full. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2013-04-18 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | CMSC ISA 4/25/11
OHA_00335 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | No procedure for annual review/revision of departmental documentation. | Potential safety issue results from inadequate or incomplete documentation. | Not Rated | Not Rated | Not Rated | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Not Rated |  |  | CMSC ISA 4/25/11
OHA_00336 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | SOPs for interepartmental coordination are not presently fully documented. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | CSMC ISA 4/25/11
OHA_00337 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | External agency coordination/communications are not fully documented. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | CSMC ISA 4/25/11
OHA_00338 | Rail | Rules Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | Departmental training policy/procedure is not formally documented. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | CSMC ISA 4/25/11
OHA_00339 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | Departmental training policy/procedure is not formally documented. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2012-09-30 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | CSMC ISA 4/25/11
OHA_00340 | Rail | Rules,Regulations,Procedures | Standard Operating Procedures | 2012-08-06 | Management methodologies are not fully documented. | Potential safety issue results from inadequate or incomplete documentation. | Remote | Negligible | Improbable | 2013-04-18 | 2012-07-31 | Completed | McCoy, Darren | Negligible | 4D - Acceptable without review | 4E - Acceptable without review | CSMC ISA 4/25/11